## Start Here
ZCare Development Checklist
Service: zimasa-zcare-service · Build order M01 → M20, one milestone (domain) at a time · Created 30 September 2026
Open the Dashboard →
How to use this workbook
1. Find the milestone | Open the Dashboard. The row marked NOW is the only milestone to work on. Every other sheet shows LOCKED until the one before it reaches 100%.
2. Work the steps in order | On that sheet, go top to bottom: 0 Gate in → 1 Data → 2 Rules → 3 API → 4 Events → 5 Screens → 6 Tests → 7 Docs → 8 Gate out. Server (BE) and screen (FE) rows of the same step may run side by side.
3. Record progress | Edit only the yellow columns: Status (drop-down), Owner, Date done and Notes / evidence (PR, test name, demo evidence file). Everything else is reference.
4. N/A counts as done | Use N/A only when a row truly does not apply, and write why in Notes.
5. Finish a milestone | At 100% the sheet shows Complete, the next sheet unlocks and the Dashboard moves NOW forward. The last Gate out row tags the release.
6. Close decisions first | The Open Decisions sheet lists conflicts and gaps found in the documents. Each Gate in row names the ones that must be Decided before that milestone starts.
7. Add a task | Type it in the first empty row below a sheet's list (Task column). Counts and progress include it automatically.
Status values
Not started | Work has not begun.
In progress | Someone is working on it now.
Blocked | Cannot continue; say what blocks it in Notes (often an Open Decision).
Done | Finished and verified; evidence in Notes.
N/A | Does not apply; reason in Notes.
Steps inside every milestone
0 Gate in | Previous milestone signed off; specs re-read; blocking decisions closed.
1 Data | JPA entities for the domain's own tables, repositories, specifications, database-error mapping.
2 Rules | Services: lifecycles, invariants and guardrails. All business logic lives here.
3 API | Controllers and DTOs for the endpoints in 04B, inside the standard envelope.
4 Events | Domain events written to the outbox; adapters behind ports.
5 Screens | Web-app screens (separate React project) for the same milestone.
6 Tests | Unit, integration (PostgreSQL as zc_app), security, consent and domain-specific tests.
7 Docs | OpenAPI/AsyncAPI, knowledge base, CHANGELOG, demo evidence.
8 Gate out | Done-when demonstrated, reviews signed, release tagged.
Team codes
Codes | BE server · FE web app · DB database · QA testing · PO product owner / delivery lead · CLIN clinician (Aga Khan) · PRIV Privacy / DPO · SEC security · OPS operations
Example of a filled-in row
# · Step · Task | Status · Owner · Date done · Notes / evidence
M07-10 · 2 Rules | ConsentGateService (one for everything) → Done · dev-a · 2026-11-18 · MR !42; ConsentGateServiceTest and ConsentGateIT green
Source key (Ref column)
RM | ZCare Migration & Development Roadmap v0.3 (docs/ZCare_Migration & Development_Roadmap_Executive_v0.3.docx.pdf)
PRD, ADD | docs/supporting docs/04-zcare_care_disease_management_PRD.md and 04-ADD-001 addendum
04A – 04F | Domain model, API & events, UX & screens (S-xx, W-x, journeys), data model, AI governance, implementation guide (docs/supporting docs)
AGENTS, GUIDE, DM | AGENTS.md / AGENT_GUARDRAILS.md, Engineering Documentation Generation Guide, DOMAIN_MODEL.md
UAT | UAT-01..28 scripts (trial repo zimasa-zcare/docs/uat/uat-scripts.md)
ADR-000n, mig-NN | Service docs/adr and src/main/resources/db/changelog/migrations/20260929_NN_*.xml
STD, LAY | Versioning & Coding Standards v1.0.0 and Project Layout & Arrangement Rules v1.0 (docs/*.pdf)
OD-nn | Open Decisions sheet in this workbook
Starting position (30 September 2026)
M01 | Mostly delivered: 60 tables, roles, RLS and append-only protection; 24 schema tests green (7 unit, 17 integration). Still open: seed data, the 04D behavioural test suite, git and CI, the web-app project, confirming design differences (R2).
M02 onwards | Not started. The Spring Boot application, API and screens arrive from M02.
Stack | Java 21, Spring Boot 3.2.2, PostgreSQL 16, Liquibase 4.24, Maven 3.9.16 (ADR-0001). Web app: React 18 + TypeScript (separate project).

## Dashboard
ZCare Development Dashboard
One milestone at a time, top to bottom. "Can start" turns Yes only when the milestone above is 100% complete; NOW marks the one to work on. Click a name to open its sheet.
Now: |  | Database Setup |  |  |  | Overall: |  | 1.444% |  | Open decisions: |  |  | 30
Order | ID | Milestone | Sprints | Depends on | Tasks | Done | Blocked | Progress | State | Can start? | Now | Open decisions | Release | Done when
1 | M01 | Database Setup | S1–S2 | — | 15 | 8 | 0 | 53.33% | In progress | Yes | NOW | 1 | v0.1.0 | The database matches the agreed design exactly, and one client cannot see another's data.
2 | M02 | Platform Foundations | S3–S5 | M01 | 33 | 0 | 0 | 0% | Not started | No |  | 12 | v0.2.0 | A user signs in and sees only what their role allows.
3 | M03 | Tenant & Access | S6–S7 | M02 | 32 | 0 | 0 | 0% | Not started | No |  | 4 | v0.3.0 | A newly created user signs in with the correct access, and no password or secret is stored in the database or shown on screen.
4 | M04 | Programme Management | S8–S10 | M03 | 30 | 0 | 0 | 0% | Not started | No |  | 2 | v0.4.0 | A programme cannot go live without clinician approval, and a published version cannot be edited.
5 | M05 | External References | S11 | M04 | 26 | 0 | 0 | 0% | Not started | No |  | 2 | v0.5.0 | Every copied detail shows its source and date, and if ZPS is down users see a clear message, never a silent gap.
6 | M06 | Population & Cohort | S12–S13 | M05 | 27 | 0 | 0 | 0% | Not started | No |  | 1 | v0.6.0 | A member sent by the payer appears as ready to invite, and a message without a valid signature is rejected, logged and changes nothing.
7 | M07 | Enrolment, Consent & Preferences | S14–S16 | M06 | 38 | 0 | 0 | 0% | Not started | No |  | 3 | v0.7.0 | No one can be activated without valid consent, and withdrawn consent blocks every action and cancels follow-on work.
8 | M08 | Assessment & Risk | S17–S18 | M07 | 29 | 0 | 0 | 0% | Not started | No |  | 2 | v0.8.0 | The same answers always give the same score, and every override has a reason.
9 | M09 | Care Planning | S19–S21 | M08 | 32 | 0 | 0 | 0% | Not started | No |  | 3 | v0.9.0 | Only a clinician activates a plan, authors cannot approve their own plans, and each member has one active plan.
10 | M10 | Care Work | S22–S23 | M09 | 32 | 0 | 0 | 0% | Not started | No |  | 2 | v0.10.0 | Each care manager has a prioritised queue that loads in under half a second at pilot scale, and overdue work is flagged.
11 | M11 | Referrals & Provider Participation | S24–S25 | M10 | 30 | 0 | 0 | 0% | Not started | No |  | 1 | v0.11.0 | A referral closes only on provider or clinician confirmation; a member's own report never closes it.
12 | M12 | Medication Coordination | S26 | M11 | 26 | 0 | 0 | 0% | Not started | No |  | 0 | v0.12.0 | A refill is "confirmed" only by a pharmacy or provider, and the database enforces it.
13 | M13 | Observation & Monitoring | S27–S28 | M12 | 29 | 0 | 0 | 0% | Not started | No |  | 4 | v0.13.0 | A reading over the limit always creates a clinician review.
14 | M14 | Care Gaps | S29–S30 | M13 | 27 | 0 | 0 | 0% | Not started | No |  | 1 | v0.14.0 | Each gap shows why it was raised, and running the check twice never creates duplicates.
15 | M15 | Engagement & Outreach | S31–S34 | M14 | 34 | 0 | 0 | 0% | Not started | No |  | 3 | v0.15.0 | "STOP" halts all contact straight away, and a consent withdrawal always wins over a message about to be sent.
16 | M16 | Outcomes & Proof | S35–S36 | M15 | 26 | 0 | 0 | 0% | Not started | No |  | 0 | v0.16.0 | Employers never see individuals, and groups under 10 are withheld, never estimated.
17 | M17 | Audit & Security | S37–S38 | M16 | 25 | 0 | 0 | 0% | Not started | No |  | 1 | v0.17.0 | History cannot be edited or deleted, and no serious security issue is open.
18 | M18 | Integration Persistence | S39–S41 | M17 | 27 | 0 | 0 | 0% | Not started | No |  | 3 | v0.18.0 | No failure is silent: every failed delivery appears as a task for an administrator.
19 | M19 | AI (switched off) | S42 | M18 | 21 | 0 | 0 | 0% | Not started | No |  | 0 | v0.19.0 | Everything works with AI switched off, and checks prove no AI is called anywhere.
20 | M20 | Testing & Acceptance | S43–S48 | M19 | 15 | 0 | 0 | 0% | Not started | No |  | 3 | v1.0.0 | All tests pass, users sign off, no serious defects remain, and the go/no-go decision is recorded.
|  | Total |  |  | 554 | 8 | 0 | 1.444%

## M01 Database
M01 · Database Setup | [8 empty] | ← Dashboard
Goal | Create the new database from the agreed design, with tenant separation built in from day one.
Owns | All 60 zc_* tables, shared functions, roles zc_app and zc_housekeeping, RLS (20 Liquibase files, 20260929_01–20)
Plan | Depends on — · Sprints S1–S2 · Screens FE-M1 web-app project · Release v0.1.0
Done when | The database matches the agreed design exactly, and one client cannot see another's data.
Progress | 53.33% | Tasks | 15 | Done or N/A | 8 | Blocked | 0 | State | In progress
READY: first milestone, no prerequisite. Work the steps in order, 0 Gate in to 8 Gate out.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M01-01 | 0 Gate in | Agree db.sql V001–V005 as the baseline | Baseline recorded, with the trial's real V003 replacing the design V003. | DB, PO | ADR-0004 | Done |  |  | ADR-0004 accepted 29 Sep 2026
M01-02 | 0 Gate in | Settle design differences with today's system | Confirm reply-message categories, WhatsApp settings and other R2 items; record each outcome. | DB, PO | RM R2; ADR-0004 | Not started
M01-03 | 1 Data | Changelog with one file per concern | 20 XML changesets carrying PostgreSQL SQL; master holds includes only; HALT preconditions and rollbacks everywhere. | DB | ADR-0003; LAY DB-02..10 | Done |  |  | ChangelogConventionsTest 7/7 green (30 Sep)
M01-04 | 1 Data | Shared functions and triggers | zc_current_tenant, zc_touch_row, zc_forbid_change, zc_forbid_pinned_change, zc_forbid_published_version_change. | DB | mig-01 | Done |  |  | mig-01
M01-05 | 1 Data | Application and housekeeping roles | zc_app owns nothing, cannot DELETE/TRUNCATE or bypass RLS; zc_housekeeping NOLOGIN. | DB | mig-02; 04D §12.4 | Done |  |  | ApplicationRolePostureIT 6/6 green
M01-06 | 1 Data | Row-level security on tenant tables | Forced RLS policy on 56 tenant tables; exempt: zc_tenant, zc_tenant_whatsapp, zc_user, zc_security_event. | DB | docs/database/README.md; mig-20 | Done |  |  | TenantIsolationIT 7/7 green
M01-07 | 1 Data | Append-only tables | 9 tables protected by trigger and privilege (config history, responses, risk, plan review, assignment history, provider action, report snapshot, audit, security event). | DB | 04D §11 | Done |  |  | ApplicationRolePostureIT
M01-08 | 1 Data | Seed data: sample programmes and test people | Liquibase context "seed"/"test-data": diabetes and workplace-wellness programmes, synthetic members marked [SYNTHETIC]; never loaded for a real tenant. | DB, CLIN | RM BE-M1; 04F §19; LAY DB-16 | Not started
M01-09 | 5 Screens | FE-M1: web-app project | Separate React 18 + TypeScript + Vite + MUI + Tailwind project with Zimasa tokens; builds automatically; Keycloak client registered. | FE | RM FE-M1 | Not started |  |  | Outside this repository; status unknown
M01-10 | 6 Tests | Rebuild from scratch equals the agreed design | Changelog and agreed-design SQL produce identical catalogues; re-running changes nothing. | DB | RM BE-M1 | Done |  |  | AgreedDesignParityIT 1/1, ChangelogMigrationIT 3/3
M01-11 | 6 Tests | 04D behavioural invariant suite | Promote the 04D §25.1 assertions still missing: T1–T12, T14, P1–P4 (incl. P4 vocabulary sweep), G1–G5. | DB, QA | 04D §25.1; 04F §18 | Not started
M01-12 | 7 Docs | Database docs | docs/database/README.md, migration-plan.md, guides/local-setup.md, compose file and setup scripts. | DB | LAY DOC | Done |  |  | Present in repo
M01-13 | 7 Docs | Put the service under git with CI | Create the repository, protect main, name the canonical remote; CI runs ./mvnw verify on every commit. | BE, OPS | STD BRN-01, BRN-08; 04F §18; OD-06 | Not started |  |  | Directory is not a git repository yet
M01-14 | 8 Gate out | Done-when demonstrated | The database matches the agreed design exactly, and one client cannot see another's data. | PO | RM §3 | Not started
M01-15 | 8 Gate out | Release v0.1.0 tagged | Annotated tag from a green pipeline; CHANGELOG created with the first section. | BE | STD REL-01, REL-03 | Not started

## M02 Platform
M02 · Platform Foundations | [8 empty] | ← Dashboard
Goal | Shared plumbing every feature relies on: sign-in, permissions, one response format, errors, idempotency, audit and outbox writers.
Owns | Packages config, security, tenant, common (no tables of their own)
Plan | Depends on M01 · Sprints S3–S5 · Screens FE-M2 sign-in, role menus, shared components · Release v0.2.0
Done when | A user signs in and sees only what their role allows.
Progress | 0% | Tasks | 33 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M01 Database first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M02-01 | 0 Gate in | Confirm M01 is signed off | Dashboard shows M01 at 100%. | PO | RM §2.2 | Not started
M02-02 | 0 Gate in | Close the open decisions needed here | OD-01 to OD-08, OD-10, OD-11, OD-18 and OD-28 marked Decided, each with an ADR (start with ADR-0005 response style). | PO, BE | OD sheet | Not started
M02-03 | 1 Data | Add dependencies with their first use | Starters web, validation, data-jpa, security, oauth2-resource-server, actuator; MapStruct, springdoc; runtime postgresql and liquibase. Versions from the Boot BOM only. | BE | LAY BLD-03, BLD-07; STD DEP-01 | Not started
M02-04 | 1 Data | Application class and configuration | ZimasaZcareApplication; application.yml (production-safe), -local, -test; every value from ${VAR}; .env.example complete. | BE | LAY CFG-01..06; STD RUN-03 | Not started
M02-05 | 1 Data | Datasource and JPA settings | Connect as zc_app; migrations run by the owner account; ddl-auto=validate; open-in-view=false. | BE | 04D §12.4; STD SCH-07, JPA-04 | Not started
M02-06 | 1 Data | Tenant context per transaction | Tenant from the token; set_config('zcare.tenant_id', id, true) at transaction start; cleared in finally; copied to async threads. | BE | tenant/package-info; 04F §9; STD RES-10 | Not started
M02-07 | 2 Rules | Audit writer | Every material write adds a zc_domain_audit row; its operation equals the envelope auditTrail.operation. | BE | 04A INV-7; 04B §5; OD-08 | Not started
M02-08 | 2 Rules | Security-event writer | Denials, tenant violations and invalid webhook signatures written to zc_security_event. | BE | 04D §11 | Not started
M02-09 | 2 Rules | Idempotency middleware | Idempotency-Key on every mutation; (key, user, route) kept at least 24 h; replay returns the same envelope; different body gives IDEMPOTENCY_KEY_CONFLICT. | BE | 04B §7; 04D §18 | Not started
M02-10 | 2 Rules | Transactional outbox writer | Domain events written in the same transaction as the aggregate; one aggregate per transaction. | BE | 04A §15; 04D §17 | Not started
M02-11 | 2 Rules | Consent-gate extension point | One ConsentGate interface called at command, dispatch and query; implementation lands in M07. | BE | 04D §9.4; RM BE-M7 | Not started
M02-12 | 3 API | Response envelope | ENG-STD-SB-001 8 fields; data never a bare array; 1-based PagedResponse; nextActions allow-list. | BE | 04B §5, §8; OD-01 | Not started
M02-13 | 3 API | Global exception handler and code registry | Business exceptions return HTTP 200 status=exception with ApiException; ZCareExceptionCodes registry (never rename a code); 401/403 only from filters. | BE | 04B §6 | Not started
M02-14 | 3 API | Validation errors per field | One VALIDATION_FIELD_INVALID/REQUIRED entry per failed field; never 422. | BE | 04B §6 | Not started
M02-15 | 3 API | Security filter chain | OAuth2 resource server with Keycloak; full JWT validation (exp, iss, aud); 8 roles mapped; unregistered route returns 403 (fail closed). | BE, SEC | RM BE-M2; STD SEC-01, SEC-02 | Not started
M02-16 | 3 API | Correlation and base path | X-Correlation-Id in, out, in MDC and on events; versioned base path defined once. | BE | 04B §4, §9; OD-03 | Not started
M02-17 | 3 API | OpenAPI from code | springdoc; info.version from the build; export compared with openapi/zcare-openapi.yaml in CI. | BE | STD API-06; 04F §9; OD-18 | Not started
M02-18 | 3 API | Operability basics | Liveness and readiness probes, graceful shutdown, structured JSON logs with an allow-list (no PHI). | BE, OPS | STD RUN-05, RUN-06, LOG-02, LOG-04; 04D §13 | Not started
M02-19 | 4 Events | Event envelope | event_id, tenant_id, correlation_id, occurred_at, aggregate_id, payload, data_classification. | BE | 04B §12; OD-28 | Not started
M02-20 | 5 Screens | FE-M2: sign-in and role menus | oidc-client-ts sign-in/out; drawer groups gated by the 7 staff roles; routes 403 independently of menus. | FE | RM FE-M2; 04C §3 | Not started
M02-21 | 5 Screens | FE-M2: shared building blocks | StatusBadge, DataTable (1-based adapter), ConsentGate, ProvenanceBadge, ReasonDialog, ApprovalHistory, EmptyState; API types generated from OpenAPI. | FE | 04C §17.3; 04F §11 | Not started
M02-22 | 6 Tests | Architecture tests (ArchUnit) | controllers → services → repositories only; no cross-domain repositories or entities; infrastructure never depends on domains; no field injection or System.out; @PreAuthorize on every endpoint. | BE | ADR-0002 r6; STD QA-03 | Not started
M02-23 | 6 Tests | Contract tests | Envelope on every route; idempotency replay and conflict; per-field validation entries. | BE, QA | 04F §18 | Not started
M02-24 | 6 Tests | Security tests | Unknown route 403; cross-tenant attempt refused and logged; expired token 401. | BE, QA | RM BE-M2; STD QA-04 | Not started
M02-25 | 6 Tests | No-PHI-in-logs test | A leak test fails the build if a log line carries a non-allow-listed field. | BE, QA | 04F §21 | Not started
M02-26 | 6 Tests | FE accessibility checks | Vitest and jest-axe on every building block. | FE | RM FE-M2 | Not started
M02-27 | 7 Docs | Architecture decisions recorded | ADRs for response style, tenant source, base path, ports home, cross-cutting writers, Boot version. | BE | LAY DOC-06; OD sheet | Not started
M02-28 | 7 Docs | SECURITY_MODEL.md | Auth, roles, RLS, tenant context and webhook signing described. | BE, SEC | 04F §20; 04A §18 | Not started
M02-29 | 7 Docs | CI pipeline and container image | Pipeline: format, enforcer, tests, secret scan, image; Dockerfile packages the tested jar; compose adds the service. | BE, OPS | STD C.5, C.6; 04F §24 | Not started
M02-30 | 7 Docs | CHANGELOG and README release section | CHANGELOG [Unreleased]; README explains release steps. | BE | STD REL-03, VER-07 | Not started
M02-31 | 8 Gate out | Done-when demonstrated | A user signs in and sees only what their role allows; each role sees the right menu. | PO | RM §3 | Not started
M02-32 | 8 Gate out | Reviews signed off | Code review; security review of the filter chain and tenant context. | SEC, PO | 04F §27 | Not started
M02-33 | 8 Gate out | Release v0.2.0 tagged | Annotated tag from a green pipeline; Dashboard shows 100%. | BE | STD REL-01, REL-04 | Not started

## M03 Access
M03 · Tenant & Access | [8 empty] | ← Dashboard
Goal | Administrators manage client organisations, staff accounts, roles, settings and each client's WhatsApp number.
Owns | domains.access: zc_tenant, zc_organisation, zc_role_assignment, zc_break_glass_grant, zc_config_history, zc_user, zc_tenant_whatsapp (mig-03)
Plan | Depends on M02 · Sprints S6–S7 · Screens S-18 · Release v0.3.0
Done when | A newly created user signs in with the correct access, and no password or secret is stored in the database or shown on screen.
Progress | 0% | Tasks | 32 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M02 Platform first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M03-01 | 0 Gate in | Confirm M02 is signed off | Dashboard shows M02 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M03-02 | 0 Gate in | Re-read this domain's specs | PRD §6.9, §8.15, §9.2; 04A §17–18; 04B §2; 04C S-18, §9, §12; ADD A9; mig-03. | BE, FE | AGENTS "Source precedence" | Not started
M03-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-12, OD-13, OD-14, OD-16 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M03-04 | 1 Data | Map owned tables to JPA entities | zc_tenant, zc_organisation, zc_role_assignment, zc_break_glass_grant, zc_config_history, zc_user, zc_tenant_whatsapp. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-03; 04D §11; ADR-0002 | Not started
M03-05 | 1 Data | Map append-only tables as insert-only | zc_config_history: INSERT and SELECT only; a change is a new row (trigger and privilege already enforce it). | BE | 04D §11; mig-20 | Not started
M03-06 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M03-07 | 1 Data | Translate constraint violations to exception codes | uq_zc_role_assignment_no_overlap → overlapping grant (WARNING); append-only config history → ZCARE_CONFIG_HISTORY_IMMUTABLE. | BE | 04D §9.3; 04B §6 | Not started
M03-08 | 2 Rules | Migration: remove secrets from the database | New changeset: zc_user without password_hash; zc_tenant_whatsapp stores a secret reference, not the access token. Update the agreed-design fixture. | DB | RM §1.1; ADR-0004; OD-12, OD-13 | Not started
M03-09 | 2 Rules | Staff accounts in Keycloak | Create users through the Keycloak Admin API; keep only a local copy of role and organisation; provider users carry the org claim. | BE | RM BE-M3; ADD A9 | Not started
M03-10 | 2 Rules | Organisations | Create, suspend, inactivate; code unique per tenant. | BE | ZCR-ADM-001; mig-03 | Not started
M03-11 | 2 Rules | Role grants | Time-bound grants; no overlapping grant; revocation needs who, when and reason. | BE | mig-03 ck_…_revocation | Not started
M03-12 | 2 Rules | Break-glass access | Reason and typed confirmation required; expires by itself; every use written as break_glass_use. | BE, SEC | PRD §9.2; 04C §8, §12 | Not started
M03-13 | 2 Rules | Admin is not health access | platform_admin without an active break-glass grant gets 403 plus a security event on any health route. | BE, SEC | ZCR-ADM-003; UC-ZC-010 D1 | Not started
M03-14 | 2 Rules | Configuration history and feature flags | Versioned, approved, effective-dated settings; no retrospective edit; feature flags stored as scope "features". | BE | ZCR-ADM-002, ADM-004; 04F §13 | Not started
M03-15 | 2 Rules | WhatsApp number per tenant | Phone number id per tenant; token held only in the server secret store; never returned by the API. | BE, SEC | RM BE-M3 | Not started
M03-16 | 2 Rules | Tenant provisioning path | Implement the decided route for creating tenants (zc_app has SELECT only on zc_tenant). | BE, OPS | OD-14 | Not started
M03-17 | 3 API | Administration endpoints | Organisations, users, role grants, break-glass grants, configuration, WhatsApp set-up; add them to 04B and OpenAPI first. | BE | OD-16; 04B §4 | Not started
M03-18 | 4 Events | Audit every admin change | Each change writes zc_domain_audit with a reason; break-glass use also writes zc_security_event. | BE | PRD §8.15; 04D §11 | Not started
M03-19 | 5 Screens | S-18 Administration | Users, roles, organisations, settings, WhatsApp set-up; reason and typed confirmation for break-glass. | FE | 04C S-18, §8 | Not started
M03-20 | 5 Screens | Break-glass banner | Persistent banner naming who authorised access and when it expires. | FE | 04C §12 | Not started
M03-21 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M03-22 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M03-23 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M03-24 | 6 Tests | New user signs in with correct access | End-to-end with Keycloak (Testcontainers or test realm): created user gets exactly the granted menus and routes. | QA | RM FE-M3 | Not started
M03-25 | 6 Tests | No secret stored or shown | Sweep test: no secret column values in the database; API responses never contain tokens. | BE, SEC | RM BE-M3 | Not started
M03-26 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M03-27 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-ADM-001..004, ZCR-SEC-001/002. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M03-28 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M03-29 | 7 Docs | Demo journey evidence committed | Evidence of Journey 17 (administer roles and access) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M03-30 | 8 Gate out | Done-when demonstrated | A newly created user signs in with the correct access, and no password or secret is stored in the database or shown on screen. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M03-31 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code; security review of break-glass and secrets handling. | SEC, PO | 04F §27, §30 | Not started
M03-32 | 8 Gate out | Release v0.3.0 tagged | Annotated tag v0.3.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M04 Programme
M04 · Programme Management | [8 empty] | ← Dashboard
Goal | Programme teams design care programmes, and a clinician approves them before use.
Owns | domains.programme: zc_programme, zc_programme_version, zc_assessment_template(_version), zc_gap_rule, zc_task_template, zc_referral_type, zc_observation_type, zc_goal_type, zc_outcome_definition (mig-05)
Plan | Depends on M03 · Sprints S8–S10 · Screens S-07 · Release v0.4.0
Done when | A programme cannot go live without clinician approval, and a published version cannot be edited.
Progress | 0% | Tasks | 30 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M03 Access first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M04-01 | 0 Gate in | Confirm M03 is signed off | Dashboard shows M03 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M04-02 | 0 Gate in | Re-read this domain's specs | PRD §8.2, §9.10; 04A §7.1; 04B §10 (publish); 04C S-07; 04D §2.3, §20; ADD Part E; mig-05. | BE, FE | AGENTS "Source precedence" | Not started
M04-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-15, OD-16, OD-17 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M04-04 | 1 Data | Map owned tables to JPA entities | zc_programme, zc_programme_version, zc_assessment_template(_version), zc_gap_rule, zc_task_template, zc_referral_type, zc_observation_type, zc_goal_type, zc_outcome_definition. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-05; 04D §11; ADR-0002 | Not started
M04-05 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M04-06 | 1 Data | Translate constraint violations to exception codes | trg_zc_programme_version_immutable → ZCARE_PROGRAMME_VERSION_IMMUTABLE; ck_…_publication → ZCARE_CLINICAL_APPROVAL_REQUIRED. | BE | 04D §9.3; 04B §6 | Not started
M04-07 | 2 Rules | Programme and version lifecycles | Programme draft → active → suspended → retired; version draft → pending_approval → published → retired. | BE | mig-05; DM | Not started
M04-08 | 2 Rules | Clinical approval gate | Publish only after a clinician records approval; otherwise ZCARE_CLINICAL_APPROVAL_REQUIRED (HARD_STOP). | BE | ZCR-PRG-004; ADD Part E | Not started
M04-09 | 2 Rules | Published versions are frozen | A material change creates a new version; the trigger rejects edits and the service refuses them first. | BE | ZCR-PRG-005/006; 04A INV-3 | Not started
M04-10 | 2 Rules | Freeze child configuration too | Templates, gap rules, task/observation/goal types and outcome definitions of a published version are refused in code (DB does not protect them). | BE | 04D §2.3, §20 | Not started
M04-11 | 2 Rules | Suspend and retire safely | Suspend new enrolments; retire with typed confirmation; never delete participation history. | BE | ZCR-PRG-007; 04C §8 | Not started
M04-12 | 2 Rules | Vocabulary as data | Care models, codes and types seeded as rows, never as CHECK constraints; care_model free text until OD-15 closes. | BE | 04D §2.3 (P4); OD-15 | Not started
M04-13 | 2 Rules | Synthetic diabetes programme v1 | HbA1c, fasting glucose, BP types; gap rules, task templates, questionnaire and outcomes marked [SYNTHETIC] until the Aga Khan package arrives. | BE, CLIN | RM BE-M4; RM R6 | Not started
M04-14 | 3 API | POST /programmes/{id}/publish | Programme admin; refused without recorded clinical approval. | BE | 04B §10 | Not started
M04-15 | 3 API | POST /programmes/{id}:record-clinical-approval | Clinician only (403 for others); records approver and time. | BE | ADD Part E; US-CLN-06 | Not started
M04-16 | 3 API | Draft authoring endpoints | Create/update programme, version, templates, rules and types while in draft; define in 04B/OpenAPI first. | BE | OD-16 | Not started
M04-17 | 4 Events | ProgrammePublished, ProgrammeRetired | Written to the outbox in the same transaction. | BE | 04B §12; ADD A11 | Not started
M04-18 | 5 Screens | S-07 Programme Configuration | Set-up screens and questionnaire builder; immutable history; reason for configuration correction. | FE | 04C S-07 | Not started
M04-19 | 5 Screens | Clinician approval page | Approval is the publish gate; retirement needs typed confirmation. | FE | 04C S-07, §8 | Not started
M04-20 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M04-21 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M04-22 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M04-23 | 6 Tests | Publication rules | Publish without approval refused; edit of a published version or its child config refused; non-clinician approval 403. | BE, QA | RM BE-M4 | Not started
M04-24 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M04-25 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-PRG-001..007, ZCR-CFG-001. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M04-26 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M04-27 | 7 Docs | Demo journey evidence committed | Evidence of Journey 1 (create and approve a programme) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M04-28 | 8 Gate out | Done-when demonstrated | A programme cannot go live without clinician approval, and a published version cannot be edited. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M04-29 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code; clinical review of the approval flow (Aga Khan). | CLIN, PO | 04F §27, §30 | Not started
M04-30 | 8 Gate out | Release v0.4.0 tagged | Annotated tag v0.4.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M05 Reference
M05 · External References | [8 empty] | ← Dashboard
Goal | Keep only the minimum details about members from outside systems, clearly marked as copies.
Owns | domains.reference: zc_member_reference, zc_external_reference (mig-04)
Plan | Depends on M04 · Sprints S11 · Screens Members list, member header · Release v0.5.0
Done when | Every copied detail shows its source and date, and if ZPS is down users see a clear message, never a silent gap.
Progress | 0% | Tasks | 26 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M04 Programme first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M05-01 | 0 Gate in | Confirm M04 is signed off | Dashboard shows M04 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M05-02 | 0 Gate in | Re-read this domain's specs | PRD §12.1–12.6, §10.5; 04A §9, §13–14, §20; 04B §13; 04C §10.4; mig-04. | BE, FE | AGENTS "Source precedence" | Not started
M05-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-09 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M05-04 | 1 Data | Map owned tables to JPA entities | zc_member_reference, zc_external_reference. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-04; 04D §11; ADR-0002 | Not started
M05-05 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M05-06 | 1 Data | Translate constraint violations to exception codes | Unique reference per (source_system, member number, individual) → duplicate absorbed; ck_…_non_auth → copies can never be authoritative. | BE | 04D §9.3; 04B §6 | Not started
M05-07 | 2 Rules | Minimum copy only | Name, phone, payer number plus source_system and source_date; is_authoritative always false. | BE | PRD §12.6; 04A INV-9 | Not started
M05-08 | 2 Rules | Never store another system's record | No member master, benefits, claims, pre-auth, prescriptions or dispensing data. | BE | 04D §2; PRD §12.5 | Not started
M05-09 | 2 Rules | PayerPort and ZPS/Eagle adapter | Vendor-neutral port; adapter uses harness verbs identify_member and check_eligibility; no direct database access. | BE | 04B §13; ZCR-INT-003; STD INT-04 | Not started
M05-10 | 2 Rules | Resilience on the payer call | Timeouts, circuit breaker, bounded retry on reads; failure returns ZCARE_EXTERNAL_DEPENDENCY_UNAVAILABLE (WARNING, retry), never a 500. | BE | ADD A10; STD RES-02..04 | Not started
M05-11 | 2 Rules | Reference snapshot with staleness | Cache the reference snapshot; mark it stale after the agreed age. | BE | 04B §13; 04C §10.4 | Not started
M05-12 | 3 API | GET /members/{ref}/care-context (header part) | Composes the reference with ZCare records; non-health header now, consent-gated body from M07. | BE | 04B §11 | Not started
M05-13 | 3 API | Members list endpoint | Paged list of references known to ZCare with source and date; define in 04B first. | BE | OD-16 | Not started
M05-14 | 5 Screens | Members list and member header | ProvenanceBadge (source, date) on every copied detail; "Stale reference" badge. | FE | RM FE-M5; 04C §10.4 | Not started
M05-15 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M05-16 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M05-17 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M05-18 | 6 Tests | ZPS double (WireMock) | Up, slow and down cases; down shows the clear message and changes nothing. | BE, QA | RM BE-M5; STD QA-07 | Not started
M05-19 | 6 Tests | Forbidden-data sweep | Test fails if a table stores claims, benefits or prescription fields. | BE | 04D §2 | Not started
M05-20 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M05-21 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-DAT-001, ZCR-INT-001, ZCR-INT-003, ZCR-PRI-001. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M05-22 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M05-23 | 7 Docs | Demo journey evidence committed | Evidence of members list with provenance badges and a ZPS-down message under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M05-24 | 8 Gate out | Done-when demonstrated | Every copied detail shows its source and date, and if ZPS is down users see a clear message, never a silent gap. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M05-25 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code. | PO | 04F §27, §30 | Not started
M05-26 | 8 Gate out | Release v0.5.0 tagged | Annotated tag v0.5.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M06 Cohort
M06 · Population & Cohort | [8 empty] | ← Dashboard
Goal | Receive eligible members from the payer and group them, reviewed, ready for invitation.
Owns | domains.cohort: zc_cohort, zc_cohort_run, zc_cohort_membership (mig-06)
Plan | Depends on M05 · Sprints S12–S13 · Screens S-08 · Release v0.6.0
Done when | A member sent by the payer appears as ready to invite, and a message without a valid signature is rejected, logged and changes nothing.
Progress | 0% | Tasks | 27 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M05 Reference first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M06-01 | 0 Gate in | Confirm M05 is signed off | Dashboard shows M05 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M06-02 | 0 Gate in | Re-read this domain's specs | PRD §8.3; 04A §7.2 (DEC-003); 04B §10; 04C S-08; ADD A10–A11; mig-06. | BE, FE | AGENTS "Source precedence" | Not started
M06-03 | 1 Data | Map owned tables to JPA entities | zc_cohort, zc_cohort_run, zc_cohort_membership. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-06; 04D §11; ADR-0002 | Not started
M06-04 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M06-05 | 1 Data | Translate constraint violations to exception codes | uq membership → repeat identification absorbed; pending_review run → ZCARE_COHORT_REVIEW_REQUIRED (ESCALATE). | BE | 04D §9.3; 04B §6 | Not started
M06-06 | 2 Rules | Cohort lifecycle | Per programme version: draft → active → closed. | BE | mig-06 | Not started
M06-07 | 2 Rules | Condition-agnostic identification | Core asks PayerPort for members flagged with the programme condition; Eagle adapter matches AilmentType Diabetes and Diabeties, never ICD codes. | BE | 04A §7.2, §20; 04B §21 | Not started
M06-08 | 2 Rules | Hold implausible volumes | Run goes to pending_review with a hold reason; a person releases or rejects it. | BE | UC-ZC-011 E2; mig-06 | Not started
M06-09 | 2 Rules | Membership provenance | Inclusion method, reason and source date on every member; removal needs a reason; history kept. | BE | ZCR-COH-003 | Not started
M06-10 | 2 Rules | Membership is not enrolment | Admin review and release before any contact; auto-invite setting off by default. | BE | ZCR-COH-004; RM BE-M6 | Not started
M06-11 | 2 Rules | Signed payer webhooks | /webhooks/payer/* (new members, leavers, reconciliations) verified with HMAC-SHA256; duplicates absorbed via the inbox. | BE, SEC | RM BE-M6; 04D §17 | Not started
M06-12 | 3 API | POST /cohorts, /cohorts/{id}/members, /cohorts/{id}:identify | Programme admin; identify returns the run and its review state. | BE | 04B §10 | Not started
M06-13 | 3 API | Review and release endpoint | Release or reject a pending run with a reason; define in 04B first. | BE | OD-16 | Not started
M06-14 | 4 Events | CohortMemberIdentified | One per match, with inclusionMethod and inclusionSourceDetail; via the outbox. | BE | 04B §12; ADD A11 | Not started
M06-15 | 5 Screens | S-08 Cohort Review & Release | Source strength per member; the 14.7% diagnosis-blind statement; release only after review; "ready to invite" cards. | FE | 04C S-08 | Not started
M06-16 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M06-17 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M06-18 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M06-19 | 6 Tests | Identification cases | Both spellings matched; repeat run absorbed; volume hold; payer down path. | BE, QA | 04A §7.2; UAT-01 | Not started
M06-20 | 6 Tests | Forged webhook | Invalid signature → 401, security event, zero state change. | BE, SEC | RM BE-M6; UAT-16 | Not started
M06-21 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M06-22 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-COH-001..004. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M06-23 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M06-24 | 7 Docs | Demo journey evidence committed | Evidence of Journey 2 (identify, review and release a cohort) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M06-25 | 8 Gate out | Done-when demonstrated | A member sent by the payer appears as ready to invite, and a message without a valid signature is rejected, logged and changes nothing. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M06-26 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code. | PO | 04F §27, §30 | Not started
M06-27 | 8 Gate out | Release v0.6.0 tagged | Annotated tag v0.6.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M07 Enrolment
M07 · Enrolment, Consent & Preferences | [8 empty] | ← Dashboard
Goal | Invite members, record their consent and start their care, never without consent.
Owns | domains.enrolment: zc_enrolment, zc_consent_record, zc_member_preference (mig-07)
Plan | Depends on M06 · Sprints S14–S16 · Screens S-02, S-06, S-15, S-16 · Release v0.7.0
Done when | No one can be activated without valid consent, and withdrawn consent blocks every action and cancels follow-on work.
Progress | 0% | Tasks | 38 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M06 Cohort first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M07-01 | 0 Gate in | Confirm M06 is signed off | Dashboard shows M06 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M07-02 | 0 Gate in | Re-read this domain's specs | PRD §8.4; 04A §7.3, §16, §22.1; 04B §10 (enrolments), §6; 04C S-02, S-06, S-15, S-16, W-1; ADD A1–A5, D; mig-07. | BE, FE | AGENTS "Source precedence" | Not started
M07-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-16, OD-19, OD-30 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M07-04 | 1 Data | Map owned tables to JPA entities | zc_enrolment, zc_consent_record, zc_member_preference. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-07; 04D §11; ADR-0002 | Not started
M07-05 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M07-06 | 1 Data | Translate constraint violations to exception codes | uq_zc_enrolment_one_active → ZCARE_ENROLMENT_DUPLICATE (WARNING); trg_zc_enrolment_pins → programme version fixed at invitation. | BE | 04D §9.3; 04B §6 | Not started
M07-07 | 2 Rules | Invite | Eligibility check via PayerPort; enrolment created as invited with the programme version pinned; eligibility snapshot kept non-authoritative. | BE | ZCR-ENR-001, ENR-004; 04A §22.1 | Not started
M07-08 | 2 Rules | Enrolment lifecycle | invited → active → suspended → completed → withdrawn; one active enrolment per member and programme; exit needs reason and date; history never deleted. | BE | ZCR-ENR-005..007; 04A INV-1 | Not started
M07-09 | 2 Rules | Consent record | captured → validated → revoked / scope_reduced / superseded; one in force; wording version and channel; revocation keeps the verbatim text. | BE | mig-07; DEC-021 | Not started
M07-10 | 2 Rules | ConsentGateService (one for everything) | Checked when acting, sending and viewing; missing → ZCARE_CONSENT_REQUIRED (ESCALATE, request_consent); revoked → ZCARE_CONSENT_REVOKED (HARD_STOP); never a 409. | BE | RM BE-M7; 04B §2, §6; 04D §9.4 | Not started
M07-11 | 2 Rules | Activation by the care manager | Never automatic on consent; needs validated consent and a responsible care manager; nextActions create_care_plan, assign_task; audit ACTIVATE_ENROLMENT. | BE | 04B §20; 04C J3 | Not started
M07-12 | 2 Rules | Suspend and withdraw | Mandatory reason; exit cancels open work and refills with a truthful label (consent_revoked or enrolment_ended), via events consumed in M10/M12. | BE | ADD A1, A2 | Not started
M07-13 | 2 Rules | Assisted consent | Care manager may record it, but it cannot validate or activate until the Privacy approval record exists; assisted revocation emits ConsentRevoked. | BE, PRIV | ADD A3, A4 | Not started
M07-14 | 2 Rules | Contact preferences | Do-not-contact (reason and time), channel, language, quiet hours, opted-out content classes. | BE | ZCR-OUT-003; mig-07 | Not started
M07-15 | 2 Rules | Audited viewing, no clinical data before consent | Every member-context view writes VIEW_MEMBER_CONTEXT; enrolment holds identity and programme context only. | BE | RM BE-M7; ADD D | Not started
M07-16 | 2 Rules | Invitation dispatch via a stub | Condition-neutral invitation sent through OutreachPort using the no-op adapter until M15. | BE | STD INT-04, RES-06; 04A §22.1 | Not started
M07-17 | 3 API | POST /enrolments:invite | Care manager. | BE | 04B §10 | Not started
M07-18 | 3 API | POST /enrolments/{id}/consent:capture | Member (via WhatsApp, from M15) or care manager (assisted). | BE | 04B §10 | Not started
M07-19 | 3 API | POST /enrolments/{id}:activate, :suspend, :withdraw | Care manager; activate requires valid consent; suspend and withdraw require a reason. | BE | 04B §10, §20 | Not started
M07-20 | 3 API | GET /enrolments?filter[status]= | Paged thin projection. | BE | 04B §11 | Not started
M07-21 | 3 API | Preferences and consent re-prompt endpoints | Not in 04B yet; define before building. | BE | OD-16 | Not started
M07-22 | 4 Events | Enrolment and consent events | EnrolmentInvited, ConsentCaptured (PHI), ConsentValidated, ConsentRevoked, EnrolmentActivated, EnrolmentSuspended, EnrolmentWithdrawn. | BE | 04B §12 | Not started
M07-23 | 5 Screens | S-06 Member 360 | Non-health header always visible; body consent-gated; REQUIRED shows "Send consent prompt"; REVOKED shows no buttons; "Access to this record is logged". | FE | 04C S-06 | Not started
M07-24 | 5 Screens | S-02 Enrolment & Consent | CM-confirmed activation; ReasonDialog for suspend/withdraw; typed confirmation for withdrawal. | FE | 04C S-02 | Not started
M07-25 | 5 Screens | S-15 Consent Record and S-16 Preferences | Six consent states, verbatim in a blockquote, wording version, DPO export; preference fields. | FE | 04C S-15, S-16 | Not started
M07-26 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M07-27 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M07-28 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M07-29 | 6 Tests | Consent-gate tests | Without valid consent every command, dispatch and query path returns ZCARE_CONSENT_REQUIRED or ZCARE_CONSENT_REVOKED (HTTP 200 exception). | BE, QA | 04D §9.4; 04F §18 | Not started
M07-30 | 6 Tests | Activation rules | No activation without validated consent; duplicate enrolment gives WARNING; withdrawn consent blocks every action. | BE, QA | UAT-02..04 | Not started
M07-31 | 6 Tests | Assisted consent blocked without Privacy record | Validation and activation refused until the approval record exists. | BE | ADD A4 | Not started
M07-32 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M07-33 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-ENR-001..007, ZCR-OUT-003, ZCR-PRI-001. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M07-34 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M07-35 | 7 Docs | Demo journey evidence committed | Evidence of Journeys 3, 4 and 20 (invite, consent, activate, withdraw) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M07-36 | 8 Gate out | Done-when demonstrated | No one can be activated without valid consent, and withdrawn consent blocks every action and cancels follow-on work. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M07-37 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code; Privacy review of the consent record and assisted-consent flow. | PRIV, PO | 04F §27, §30 | Not started
M07-38 | 8 Gate out | Release v0.7.0 tagged | Annotated tag v0.7.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M08 Assessment
M08 · Assessment & Risk | [8 empty] | ← Dashboard
Goal | Run health questionnaires and set a priority level for each member.
Owns | domains.assessment: zc_assessment, zc_assessment_response, zc_risk_classification (mig-08)
Plan | Depends on M07 · Sprints S17–S18 · Screens S-09 · Release v0.8.0
Done when | The same answers always give the same score, and every override has a reason.
Progress | 0% | Tasks | 29 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M07 Enrolment first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M08-01 | 0 Gate in | Confirm M07 is signed off | Dashboard shows M07 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M08-02 | 0 Gate in | Re-read this domain's specs | PRD §8.5; 04A §7.4; 04B §10; 04C S-09, W-3; 04E §1; mig-08. | BE, FE | AGENTS "Source precedence" | Not started
M08-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-15, OD-16 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M08-04 | 1 Data | Map owned tables to JPA entities | zc_assessment, zc_assessment_response, zc_risk_classification. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-08; 04D §11; ADR-0002 | Not started
M08-05 | 1 Data | Map append-only tables as insert-only | zc_assessment_response, zc_risk_classification: INSERT and SELECT only; a change is a new row (trigger and privilege already enforce it). | BE | 04D §11; mig-20 | Not started
M08-06 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M08-07 | 1 Data | Translate constraint violations to exception codes | trg_zc_assessment_pins → template version fixed at assignment; ck_…_override → override needs a reason. | BE | 04D §9.3; 04B §6 | Not started
M08-08 | 2 Rules | Assessment lifecycle | assigned → in_progress → completed / cancelled / expired, pinned to the template version. | BE | mig-08 | Not started
M08-09 | 2 Rules | Append-only answers | A changed answer is a new row; the latest answer wins. | BE | ZCR-ASM-002; 04D | Not started
M08-10 | 2 Rules | Deterministic scoring | Scores from the pinned version's scoring rules only; score_detail explains the result; never scored complete when incomplete. | BE | ZCR-ASM-003; 04E §1 | Not started
M08-11 | 2 Rules | Priority, never diagnosis | Risk classification is append-only programme priority; tier names free text until OD-15 closes. | BE | ZCR-ASM-004; ADD D | Not started
M08-12 | 2 Rules | Clinician confirm or override | Override creates a new row linked to the one it overrides, with a reason. | BE | ZCR-ASM-005 | Not started
M08-13 | 2 Rules | Expiry | Expired assessments raise a care-manager task (wired when M10 lands). | BE | 04C W-3 | Not started
M08-14 | 3 API | POST /assessments/{id}:complete | Care manager or member; consent-gated. | BE | 04B §10 | Not started
M08-15 | 3 API | Assign and answer endpoints | Assign, record answers, confirm/override tier; define in 04B first. | BE | OD-16 | Not started
M08-16 | 4 Events | AssessmentCompleted, RiskClassificationChanged | Via the outbox. | BE | 04B §12 | Not started
M08-17 | 5 Screens | S-09 Assessment | Questionnaire with score; tier shown as programme priority; clinician confirm/override; validation on both surfaces. | FE | 04C S-09 | Not started
M08-18 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M08-19 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M08-20 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M08-21 | 6 Tests | Consent-gate tests | Without valid consent every command, dispatch and query path returns ZCARE_CONSENT_REQUIRED or ZCARE_CONSENT_REVOKED (HTTP 200 exception). | BE, QA | 04D §9.4; 04F §18 | Not started
M08-22 | 6 Tests | Repeatable scores | Property test: same answers and version always give the same score and tier. | BE | RM BE-M8; UAT-26 | Not started
M08-23 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M08-24 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-ASM-001..005. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M08-25 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M08-26 | 7 Docs | Demo journey evidence committed | Evidence of Journey 5 (complete an assessment) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M08-27 | 8 Gate out | Done-when demonstrated | The same answers always give the same score, and every override has a reason. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M08-28 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code. | PO | 04F §27, §30 | Not started
M08-29 | 8 Gate out | Release v0.8.0 tagged | Annotated tag v0.8.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M09 Care Plan
M09 · Care Planning | [8 empty] | ← Dashboard
Goal | Create care plans with measurable goals that a clinician approves, never the person who wrote them.
Owns | domains.careplan: zc_care_plan, zc_goal, zc_intervention, zc_care_plan_link, zc_plan_review (mig-09)
Plan | Depends on M08 · Sprints S19–S21 · Screens S-03, S-13 · Release v0.9.0
Done when | Only a clinician activates a plan, authors cannot approve their own plans, and each member has one active plan.
Progress | 0% | Tasks | 32 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M08 Assessment first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M09-01 | 0 Gate in | Confirm M08 is signed off | Dashboard shows M08 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M09-02 | 0 Gate in | Re-read this domain's specs | PRD §8.6; 04A §7.5, §22.2; 04B §10; 04C S-03, S-13; ADD A6, Part E, D; mig-09. | BE, FE | AGENTS "Source precedence" | Not started
M09-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-16, OD-17, OD-20 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M09-04 | 1 Data | Map owned tables to JPA entities | zc_care_plan, zc_goal, zc_intervention, zc_care_plan_link, zc_plan_review. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-09; 04D §11; ADR-0002 | Not started
M09-05 | 1 Data | Map append-only tables as insert-only | zc_plan_review: INSERT and SELECT only; a change is a new row (trigger and privilege already enforce it). | BE | 04D §11; mig-20 | Not started
M09-06 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M09-07 | 1 Data | Translate constraint violations to exception codes | trg_zc_care_plan_approval_immutable → ZCARE_PLAN_VERSION_IMMUTABLE; uq_zc_care_plan_one_active → one active plan; ck_zc_goal_measurable → field error naming the goal. | BE | 04D §9.3; 04B §6 | Not started
M09-08 | 2 Rules | Plan lifecycle | draft → pending_approval → active; request changes → draft; reject → rejected; then revised, suspended, completed, closed. | BE | 04A §22.2; mig-09 | Not started
M09-09 | 2 Rules | Clinician-only approval, author excluded | Approver must be a clinician and not the author (code; DB does not check); others get 403 from the filter layer. | BE, SEC | RM §1.2, BE-M9; ADD Part E | Not started
M09-10 | 2 Rules | Approval is final | Approver and time write-once; never approved by timeout; no bulk approve. | BE | mig-09; ADD D | Not started
M09-11 | 2 Rules | Measurable goals | Every goal has a target value and unit or criteria; a plan with zero goals cannot be submitted. | BE | ck_zc_goal_measurable; ADD A6 | Not started
M09-12 | 2 Rules | Revisions keep history | A revision copies goals and open interventions; the previous version keeps its approver. | BE | ZCR-CRP-004; ADD A6 | Not started
M09-13 | 2 Rules | Plan reviews | Every decision appended to zc_plan_review; notes required for anything but approved or continue_unchanged. | BE | mig-09 | Not started
M09-14 | 2 Rules | Tasks from plans via events | Submit emits the event that creates a PLAN_APPROVAL task; activation emits tasks from interventions (both consumed in M10). | BE | ADD Part E; 04A §22.2 | Not started
M09-15 | 3 API | POST /care-plans | Care manager drafts; consent-gated. | BE | 04B §10 | Not started
M09-16 | 3 API | Submit for approval | nextActions names submit_for_approval but 04B has no endpoint; define it first. | BE | OD-16 | Not started
M09-17 | 3 API | POST /care-plans/{id}:activate, :request-changes, :reject | Clinician only; request-changes and reject need notes. | BE | 04B §10; ADD Part E | Not started
M09-18 | 4 Events | CarePlanActivated, CarePlanRevised | Via the outbox; plus the submit event for the approval task. | BE | 04B §12 | Not started
M09-19 | 5 Screens | S-03 Care Plan | Goal validation naming the goal; autosave drafts; ApprovalHistory; "Awaiting approval" badge. | FE | 04C S-03 | Not started
M09-20 | 5 Screens | S-13 Clinician Approval Queue | Waiting-time column; comments for changes, reason for reject; nothing auto-advances; works at 768 px. | FE | 04C S-13 | Not started
M09-21 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M09-22 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M09-23 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M09-24 | 6 Tests | Consent-gate tests | Without valid consent every command, dispatch and query path returns ZCARE_CONSENT_REQUIRED or ZCARE_CONSENT_REVOKED (HTTP 200 exception). | BE, QA | 04D §9.4; 04F §18 | Not started
M09-25 | 6 Tests | Approval rules | Author cannot approve; care manager approval gives 403 (logged); approved fields immutable; one active plan; revision copies goals. | BE, QA | UAT-05, UAT-25 | Not started
M09-26 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M09-27 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-CRP-001..005. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M09-28 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M09-29 | 7 Docs | Demo journey evidence committed | Evidence of Journey 6 (draft, submit, clinician approval) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M09-30 | 8 Gate out | Done-when demonstrated | Only a clinician activates a plan, authors cannot approve their own plans, and each member has one active plan. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M09-31 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code; clinical review of the approval flow (Aga Khan). | CLIN, PO | 04F §27, §30 | Not started
M09-32 | 8 Gate out | Release v0.9.0 tagged | Annotated tag v0.9.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M10 Care Work
M10 · Care Work | [8 empty] | ← Dashboard
Goal | Turn plans and alerts into clear, prioritised to-do lists for the care team.
Owns | domains.carework: zc_task, zc_task_dependency, zc_task_assignment_history, zc_work_queue_definition (mig-10)
Plan | Depends on M09 · Sprints S22–S23 · Screens S-01 · Release v0.10.0
Done when | Each care manager has a prioritised queue that loads in under half a second at pilot scale, and overdue work is flagged.
Progress | 0% | Tasks | 32 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M09 Care Plan first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M10-01 | 0 Gate in | Confirm M09 is signed off | Dashboard shows M09 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M10-02 | 0 Gate in | Re-read this domain's specs | PRD §8.7; 04A §7.6; 04B §10–11; 04C S-01; ADD A1, B, E; mig-10. | BE, FE | AGENTS "Source precedence" | Not started
M10-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-16, OD-29 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M10-04 | 1 Data | Map owned tables to JPA entities | zc_task, zc_task_dependency, zc_task_assignment_history, zc_work_queue_definition. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-10; 04D §11; ADR-0002 | Not started
M10-05 | 1 Data | Map append-only tables as insert-only | zc_task_assignment_history: INSERT and SELECT only; a change is a new row (trigger and privilege already enforce it). | BE | 04D §11; mig-20 | Not started
M10-06 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M10-07 | 1 Data | Translate constraint violations to exception codes | trg_zc_task_dependency_gate → task blocked by an open prerequisite; restricted completion → ZCARE_TASK_RESTRICTED (ESCALATE, in the envelope, not 403). | BE | 04D §9.3; 04B §6 | Not started
M10-08 | 2 Rules | Task lifecycle | assigned → accepted → in_progress → blocked → completed / cancelled; priority 1–5; assignee is a person or a role. | BE | mig-10 | Not started
M10-09 | 2 Rules | Tasks from earlier domains | Consume events: PLAN_APPROVAL on plan submit, intervention tasks on plan activation, expired assessments, cancellations on enrolment exit with the right label. | BE | ADD A1, Part E | Not started
M10-10 | 2 Rules | Dependencies | A task cannot complete while a prerequisite is open; removing a dependency needs a reason. | BE | mig-10 | Not started
M10-11 | 2 Rules | Reassignment history | Every reassignment appends a row; cancel needs a reason. | BE | ZCR-WRK-004 | Not started
M10-12 | 2 Rules | Restricted task types | PLAN_APPROVAL, THRESHOLD_REVIEW and similar completable only by their role owner. | BE | UC-ZC-003 E1; ADD B | Not started
M10-13 | 2 Rules | Completion is not an outcome | Completing a task never records a clinical or programme outcome. | BE | ZCR-WRK-005 | Not started
M10-14 | 2 Rules | Deadline job | Scheduled job sets sla_state and emits TaskOverdue; SLA values from OD-29. | BE | RM BE-M10 | Not started
M10-15 | 2 Rules | Work queues as queries | Queue definitions filter zc_task; paged thin projections on the queue indexes. | BE | mig-10; 04F §8 | Not started
M10-16 | 3 API | POST /tasks, POST /tasks/{id}:complete, GET /work-queues/{role} | Care manager; queue paged 1-based. | BE | 04B §10–11 | Not started
M10-17 | 3 API | Accept, cancel, reassign, escalate | In 04C but missing from 04B; define before building. | BE | OD-16 | Not started
M10-18 | 4 Events | TaskAssigned, TaskCompleted, TaskOverdue | Via the outbox. | BE | 04B §12 | Not started
M10-19 | 5 Screens | S-01 Work Queue | Origin badges linking to the source; Blocked chip; completion copy; three empty states; responsive columns; aria-sort and aria-live. | FE | 04C S-01 | Not started
M10-20 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M10-21 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M10-22 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M10-23 | 6 Tests | Consent-gate tests | Without valid consent every command, dispatch and query path returns ZCARE_CONSENT_REQUIRED or ZCARE_CONSENT_REVOKED (HTTP 200 exception). | BE, QA | 04D §9.4; 04F §18 | Not started
M10-24 | 6 Tests | Queue performance | p95 under 500 ms at 100 times pilot synthetic volume. | QA | 04F §22; RM BE-M10 | Not started
M10-25 | 6 Tests | Cross-domain task flows | Plan submit creates PLAN_APPROVAL; enrolment exit cancels open tasks with the right label. | BE, QA | ADD A1; UAT-06, UAT-09 | Not started
M10-26 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M10-27 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-WRK-001..005. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M10-28 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M10-29 | 7 Docs | Demo journey evidence committed | Evidence of Journeys 7 and 8 (work a task from the queue) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M10-30 | 8 Gate out | Done-when demonstrated | Each care manager has a prioritised queue that loads in under half a second at pilot scale, and overdue work is flagged. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M10-31 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code. | PO | 04F §27, §30 | Not started
M10-32 | 8 Gate out | Release v0.10.0 tagged | Annotated tag v0.10.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M11 Referral
M11 · Referrals & Provider Participation | [8 empty] | ← Dashboard
Goal | Refer members to providers such as Aga Khan and track the outcome.
Owns | domains.referral: zc_referral, zc_transition, zc_provider_participation, zc_provider_action (mig-11)
Plan | Depends on M10 · Sprints S24–S25 · Screens S-11, provider screens · Release v0.11.0
Done when | A referral closes only on provider or clinician confirmation; a member's own report never closes it.
Progress | 0% | Tasks | 30 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M10 Care Work first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M11-01 | 0 Gate in | Confirm M10 is signed off | Dashboard shows M10 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M11-02 | 0 Gate in | Re-read this domain's specs | PRD §8.8, §8.14, §10.6, §12.8; 04A §7.7, §7.13, §16; 04B §10, §13–14; 04C S-11; ADD A9; mig-11. | BE, FE | AGENTS "Source precedence" | Not started
M11-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-23 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M11-04 | 1 Data | Map owned tables to JPA entities | zc_referral, zc_transition, zc_provider_participation, zc_provider_action. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-11; 04D §11; ADR-0002 | Not started
M11-05 | 1 Data | Map append-only tables as insert-only | zc_provider_action: INSERT and SELECT only; a change is a new row (trigger and privilege already enforce it). | BE | 04D §11; mig-20 | Not started
M11-06 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M11-07 | 1 Data | Translate constraint violations to exception codes | ck_zc_referral_completion → completion needs provider or clinician confirmation; uq_zc_provider_participation_live → one live participation. | BE | 04D §9.3; 04B §6 | Not started
M11-08 | 2 Rules | Referral is a coordination record | Never a clinical order; created → routed → accepted / declined → in_progress → completed / cancelled / expired. | BE | 04A §7.7; mig-11 | Not started
M11-09 | 2 Rules | Confirmation from identity | Confirmation source derived from the caller's role, never a form field; care manager cannot record provider-confirmed. | BE, SEC | ADD A9; ZCR-REF-005 | Not started
M11-10 | 2 Rules | Decline and routing | Decline needs a reason; routing needs a receiving organisation or provider reference. | BE | mig-11 | Not started
M11-11 | 2 Rules | Timeouts never close | An overdue referral raises a task and stays open. | BE | 04A §16 | Not started
M11-12 | 2 Rules | Provider participation | One live participation per programme version and organisation; actions appended; token org must match. | BE | ZCR-PRV-001..003; ADD A9 | Not started
M11-13 | 2 Rules | ProviderPort and Portal adapter | Signed provider callbacks for acceptance and outcome; timeouts and breaker; no contracting, payment or credentialing. | BE | 04B §13–14; ZCR-PRV-004 | Not started
M11-14 | 2 Rules | Transitions | notified → in_progress → completed / cancelled (scope "Could", confirm before building). | BE, PO | ZCR-REF-006 | Not started
M11-15 | 3 API | POST /referrals, POST /referrals/{id}:record-outcome | Care manager or provider coordinator; consent-gated. | BE | 04B §10 | Not started
M11-16 | 3 API | POST /provider-actions and provider callback webhook | Provider coordinator, own organisation only. | BE | 04B §10, §14 | Not started
M11-17 | 4 Events | ReferralCreated, ReferralAccepted, ReferralCompleted, ProviderActionRecorded | Via the outbox. | BE | 04B §12 | Not started
M11-18 | 5 Screens | S-11 Referrals Board and provider queue | "Unconfirmed" and "Undelivered" badges; completion only on authorised confirmation; providers see own organisation only. | FE | 04C S-11 | Not started
M11-19 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M11-20 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M11-21 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M11-22 | 6 Tests | Consent-gate tests | Without valid consent every command, dispatch and query path returns ZCARE_CONSENT_REQUIRED or ZCARE_CONSENT_REVOKED (HTTP 200 exception). | BE, QA | 04D §9.4; 04F §18 | Not started
M11-23 | 6 Tests | Completion rules | Care manager completion refused; clinician or provider completes; other-organisation provider 403. | BE, QA | UAT-24 | Not started
M11-24 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M11-25 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-REF-001..006, ZCR-PRV-001..004. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M11-26 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M11-27 | 7 Docs | Demo journey evidence committed | Evidence of Journeys 9 and 14 (provider accepts and completes) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M11-28 | 8 Gate out | Done-when demonstrated | A referral closes only on provider or clinician confirmation; a member's own report never closes it. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M11-29 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code. | PO | 04F §27, §30 | Not started
M11-30 | 8 Gate out | Release v0.11.0 tagged | Annotated tag v0.11.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M12 Medication
M12 · Medication Coordination | [8 empty] | ← Dashboard
Goal | Help members get refills on time, without prescribing or dispensing.
Owns | domains.medication: zc_medication_coordination, zc_refill_request, zc_adherence_event (mig-12)
Plan | Depends on M11 · Sprints S26 · Screens S-05 · Release v0.12.0
Done when | A refill is "confirmed" only by a pharmacy or provider, and the database enforces it.
Progress | 0% | Tasks | 26 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M11 Referral first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M12-01 | 0 Gate in | Confirm M11 is signed off | Dashboard shows M11 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M12-02 | 0 Gate in | Re-read this domain's specs | PRD §8.9, §10.9; 04A §7.8; 04B §10, §21; 04C S-05, W-4; ADD A2, D; mig-12. | BE, FE | AGENTS "Source precedence" | Not started
M12-03 | 1 Data | Map owned tables to JPA entities | zc_medication_coordination, zc_refill_request, zc_adherence_event. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-12; 04D §11; ADR-0002 | Not started
M12-04 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M12-05 | 1 Data | Translate constraint violations to exception codes | ck_zc_refill_confirmed_requires_authorised_source → ZCARE_FULFILMENT_SOURCE_REQUIRED; uq_zc_refill_one_open → ZCARE_REFILL_DUPLICATE (INFO, open the existing request). | BE | 04D §9.3; 04B §6 | Not started
M12-06 | 2 Rules | Reference the provider's plan only | plan_ref and plan_ref_system; never prescribe, alter, approve, dispense or manage stock. | BE | ZCR-MED-004 | Not started
M12-07 | 2 Rules | Refill lifecycle | requested → routed → in_progress → concluded / cancelled; one open refill per plan. | BE | mig-12 | Not started
M12-08 | 2 Rules | Member-reported is never confirmed | Pilot records member_reported only; confirmed needs a pharmacy or provider source. | BE | DEC-006; ADD D | Not started
M12-09 | 2 Rules | Overdue job | Sets is_overdue independently of status; feeds the REFILL_MISSED gap rule in M14. | BE | RM BE-M12; UAT-27 | Not started
M12-10 | 2 Rules | Adherence and medication review | Adherence events with their source; "raise medication review" creates a clinician task. | BE | PRD §8.9; 04C S-05 | Not started
M12-11 | 2 Rules | Exit cancels refills | Enrolment exit cancels open refill requests with the truthful label. | BE | ADD A2 | Not started
M12-12 | 3 API | POST /refill-requests, POST /refill-requests/{id}:record-fulfilment | Care manager (member via WhatsApp from M15); consent-gated. | BE | 04B §10 | Not started
M12-13 | 4 Events | RefillRequested, RefillFulfilled | RefillFulfilled carries confirmationSource. | BE | 04B §12 | Not started
M12-14 | 5 Screens | S-05 Medication & Refill | No "Confirmed" control; locked "Member-reported" badge; source text on every fulfilment; overdue shown. | FE | 04C S-05 | Not started
M12-15 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M12-16 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M12-17 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M12-18 | 6 Tests | Consent-gate tests | Without valid consent every command, dispatch and query path returns ZCARE_CONSENT_REQUIRED or ZCARE_CONSENT_REVOKED (HTTP 200 exception). | BE, QA | 04D §9.4; 04F §18 | Not started
M12-19 | 6 Tests | Fulfilment rules | Database rejects confirmed without an authorised source; duplicate gives INFO; overdue flagged; exit cancels. | BE, QA | UAT-22, UAT-23 | Not started
M12-20 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M12-21 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-MED-001..004. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M12-22 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M12-23 | 7 Docs | Demo journey evidence committed | Evidence of Journey 10 (request and track a refill) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M12-24 | 8 Gate out | Done-when demonstrated | A refill is "confirmed" only by a pharmacy or provider, and the database enforces it. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M12-25 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code. | PO | 04F §27, §30 | Not started
M12-26 | 8 Gate out | Release v0.12.0 tagged | Annotated tag v0.12.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M13 Observation
M13 · Observation & Monitoring | [8 empty] | ← Dashboard
Goal | Record key readings and send any reading over a limit to a clinician.
Owns | domains.observation: zc_monitoring_schedule, zc_observation (mig-13)
Plan | Depends on M12 · Sprints S27–S28 · Screens S-10, S-14 · Release v0.13.0
Done when | A reading over the limit always creates a clinician review.
Progress | 0% | Tasks | 29 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M12 Medication first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M13-01 | 0 Gate in | Confirm M12 is signed off | Dashboard shows M12 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M13-02 | 0 Gate in | Re-read this domain's specs | PRD §8.10, §10.8; 04A §7.9, INV-6; 04B §10; 04C S-10, S-14, W-5; ADD A8; mig-13. | BE, FE | AGENTS "Source precedence" | Not started
M13-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-17, OD-26 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M13-04 | 1 Data | Map owned tables to JPA entities | zc_monitoring_schedule, zc_observation. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-13; 04D §11; ADR-0002 | Not started
M13-05 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M13-06 | 1 Data | Translate constraint violations to exception codes | trg_zc_observation_correction_only → readings never edited, only invalidated; missing thresholds → ZCARE_THRESHOLD_RULES_MISSING. | BE | 04D §9.3; 04B §6 | Not started
M13-07 | 2 Rules | Programme-required observations only | Type must belong to the enrolment's programme version; unit fixed by the type (UCUM). | BE | 04A INV-6; mig-13 | Not started
M13-08 | 2 Rules | Plausibility | Values outside plausible range stored as implausible, excluded from trends, and raise a care-manager task. | BE | 04C W-5 | Not started
M13-09 | 2 Rules | Invalidate, never edit | Invalidation needs a reason, is final, and reopens dependent gap closures. | BE | ZCR-OBS-002; 04D §20 | Not started
M13-10 | 2 Rules | Threshold evaluation | In range: stored quietly. Breach: priority-1 THRESHOLD_REVIEW clinician task, event, and ZCARE_THRESHOLD_REVIEW_REQUIRED ("not a diagnosis"). | BE | ADD A8; ZCR-OBS-003 | Not started
M13-11 | 2 Rules | Monitoring schedules | Cadence per type; missing scheduled readings flagged. | BE | PRD §8.10 | Not started
M13-12 | 2 Rules | Deduplication and trend view | Dedup on type, time and source; consent-protected trend view. | BE | 04D §18; RM BE-M13 | Not started
M13-13 | 3 API | POST /observations | Care manager or clinician; consent-gated. | BE | 04B §10 | Not started
M13-14 | 3 API | Invalidate and threshold-decision endpoints | Define in 04B first. | BE | OD-16 | Not started
M13-15 | 4 Events | ObservationCaptured, ThresholdReviewRequired | Via the outbox. | BE | 04B §12 | Not started
M13-16 | 5 Screens | S-10 Observations & Trends | Units as selects; "Member-reported" and "Not evaluated" badges; implausible values excluded from the trend. | FE | 04C S-10 | Not started
M13-17 | 5 Screens | S-14 Threshold-Review Queue | Elapsed time; text summary with a hidden sparkline; record decision, invalidate, raise task, refer. | FE | 04C S-14 | Not started
M13-18 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M13-19 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M13-20 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M13-21 | 6 Tests | Consent-gate tests | Without valid consent every command, dispatch and query path returns ZCARE_CONSENT_REQUIRED or ZCARE_CONSENT_REVOKED (HTTP 200 exception). | BE, QA | 04D §9.4; 04F §18 | Not started
M13-22 | 6 Tests | Threshold cases | HbA1c 9.1 raises the review task; 7.2 is stored with no escalation. | BE, QA | UAT-20, UAT-21 | Not started
M13-23 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M13-24 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-OBS-001..004. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M13-25 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M13-26 | 7 Docs | Demo journey evidence committed | Evidence of Journey 11 (clinician reviews a flagged reading) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M13-27 | 8 Gate out | Done-when demonstrated | A reading over the limit always creates a clinician review. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M13-28 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code; clinical review of thresholds (Aga Khan). | CLIN, PO | 04F §27, §30 | Not started
M13-29 | 8 Gate out | Release v0.13.0 tagged | Annotated tag v0.13.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M14 Care Gaps
M14 · Care Gaps | [8 empty] | ← Dashboard
Goal | Spot missed care automatically, explain it, and turn it into work.
Owns | domains.caregap: zc_care_gap (mig-14)
Plan | Depends on M13 · Sprints S29–S30 · Screens S-04 · Release v0.14.0
Done when | Each gap shows why it was raised, and running the check twice never creates duplicates.
Progress | 0% | Tasks | 27 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M13 Observation first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M14-01 | 0 Gate in | Confirm M13 is signed off | Dashboard shows M13 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M14-02 | 0 Gate in | Re-read this domain's specs | PRD §8.11; 04A §7.10, INV-5, §22.3; 04B §10; 04C S-04; ADD C1–C2, D; mig-14. | BE, FE | AGENTS "Source precedence" | Not started
M14-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-21 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M14-04 | 1 Data | Map owned tables to JPA entities | zc_care_gap. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-14; 04D §11; ADR-0002 | Not started
M14-05 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M14-06 | 1 Data | Translate constraint violations to exception codes | uq_zc_care_gap_dedup → ZCARE_GAP_DUPLICATE (INFO); ck_zc_care_gap_action_reason → ZCARE_GAP_SUPPRESS_REASON_REQUIRED; role gate → ZCARE_GAP_ACTION_RESTRICTED. | BE | 04D §9.3; 04B §6 | Not started
M14-07 | 2 Rules | Deterministic rule evaluator | Versioned gap rules from the programme version; no AI. | BE | ZCR-GAP-001; 04E §1 | Not started
M14-08 | 2 Rules | GapKey deduplication | (member, programme version, gap type, period); a repeat detection is absorbed. | BE | 04A INV-5 | Not started
M14-09 | 2 Rules | Explainable gaps | Rule version, reason and evaluated data stored on every gap. | BE | ZCR-GAP-002 | Not started
M14-10 | 2 Rules | Scheduled detection job | Runs per tenant; includes the REFILL_MISSED rule. | BE | RM BE-M14; UAT-27 | Not started
M14-11 | 2 Rules | Gaps become work | Assigned gap links a task for the same member; optional outreach request. | BE | PRD §8.11 | Not started
M14-12 | 2 Rules | Suppress, close, reopen | Authorised role and reason; no batch suppression; close only on approved evidence; reopen reuses the row. | BE | ZCR-GAP-004/005; ADD D; 04D §9.2 | Not started
M14-13 | 3 API | POST /care-gaps/{id}:suppress, POST /care-gaps/{id}:close | Authorised care manager with a reason; consent-gated. | BE | 04B §10 | Not started
M14-14 | 4 Events | CareGapDetected, CareGapClosed | Detected carries rule version, reason and evaluated data. | BE | 04B §12; 04A §22.3 | Not started
M14-15 | 5 Screens | S-04 Care Gaps board | Rule version, reason and data shown; role-gated suppression with ReasonDialog; suppressed tab keeps gaps visible. | FE | 04C S-04 | Not started
M14-16 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M14-17 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M14-18 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M14-19 | 6 Tests | Consent-gate tests | Without valid consent every command, dispatch and query path returns ZCARE_CONSENT_REQUIRED or ZCARE_CONSENT_REVOKED (HTTP 200 exception). | BE, QA | 04D §9.4; 04F §18 | Not started
M14-20 | 6 Tests | Detection is idempotent and explained | Two runs, one gap; every gap has its reason; suppress without reason impossible. | BE, QA | UAT-06..08 | Not started
M14-21 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M14-22 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-GAP-001..005. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M14-23 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M14-24 | 7 Docs | Demo journey evidence committed | Evidence of Journey 12 (gap found, worked and closed) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M14-25 | 8 Gate out | Done-when demonstrated | Each gap shows why it was raised, and running the check twice never creates duplicates. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M14-26 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code. | PO | 04F §27, §30 | Not started
M14-27 | 8 Gate out | Release v0.14.0 tagged | Annotated tag v0.14.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M15 Engagement
M15 · Engagement & Outreach | [8 empty] | ← Dashboard
Goal | Contact members on WhatsApp for reminders, questionnaires and consent, and honour STOP immediately.
Owns | domains.engagement: zc_outreach_request, zc_outreach_delivery, zc_inbound_message (mig-15)
Plan | Depends on M14 · Sprints S31–S34 · Screens S-12, W-1–W-6 · Release v0.15.0
Done when | "STOP" halts all contact straight away, and a consent withdrawal always wins over a message about to be sent.
Progress | 0% | Tasks | 34 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M14 Care Gaps first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M15-01 | 0 Gate in | Confirm M14 is signed off | Dashboard shows M14 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M15-02 | 0 Gate in | Re-read this domain's specs | PRD §8.12; 04A §7.11, §16, §22.1; 04B §13–14; 04C S-12, §7.10 (W-1–W-6); ADD A5, B, D; mig-15. | BE, FE | AGENTS "Source precedence" | Not started
M15-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-13, OD-22, OD-24 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M15-04 | 1 Data | Map owned tables to JPA entities | zc_outreach_request, zc_outreach_delivery, zc_inbound_message. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-15; 04D §11; ADR-0002 | Not started
M15-05 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M15-06 | 1 Data | Translate constraint violations to exception codes | uq_zc_inbound_message_dedup → webhook redelivery absorbed; frequency limit → ZCARE_OUTREACH_FREQUENCY_EXCEEDED with the next permissible date. | BE | 04D §9.3; 04B §6 | Not started
M15-07 | 2 Rules | Outreach request | Purpose and content class; health content needs an enrolment; requested → queued → held → dispatched → delivered → completed (or failed, cancelled, suppressed). | BE | mig-15 | Not started
M15-08 | 2 Rules | Hold rules | Hold outside quiet hours or over the frequency limit; return the next permissible date. | BE | ZCR-OUT-003; RM BE-M15 | Not started
M15-09 | 2 Rules | Consent checked at the moment of sending | Dispatch re-checks consent and preferences; withdrawal always wins. | BE | 04D §9.4; 04A §22.3 | Not started
M15-10 | 2 Rules | OutreachPort and WhatsApp adapter | Meta Cloud API; 24-hour window and templates; wamid is the idempotency key; each retry a new delivery row. | BE | 04B §13 | Not started
M15-11 | 2 Rules | Signed inbound webhook | HMAC-SHA256 verified; tenant from the phone number id; invalid → 401, security event, no change. | BE, SEC | 04B §14 | Not started
M15-12 | 2 Rules | Reply interpretation | Opt-in, opt-out, ambiguous opt-out, decline, assessment answer, refill reply, task reply; unclear replies go to a person. | BE | mig-15; ADD B | Not started
M15-13 | 2 Rules | Exact STOP | Suppress first; withdraw; revoke with verbatim; cancel pending work; exactly one confirmation; SAFE_EXIT task; never re-persuade. | BE | ADD A5, D; 04C W-6 | Not started
M15-14 | 2 Rules | Ambiguous opt-out | Suppress all outreach, keep enrolment, raise priority-1 CONFIRM_OPT_OUT task. | BE | ADD A5 | Not started
M15-15 | 2 Rules | Conversations W-1 to W-5 | Condition-neutral invitation; task acknowledgement; assessment one question at a time; refill; observation echo-confirm. | BE, FE | 04C §7.10 | Not started
M15-16 | 2 Rules | ZHEP adapter, switched off | Built behind a flag that defaults to off. | BE | RM BE-M15; STD RES-06 | Not started
M15-17 | 2 Rules | Failed outreach creates follow-up work | Failed or incomplete outreach raises a task. | BE | PRD §8.12 | Not started
M15-18 | 3 API | POST /outreach-requests and WhatsApp webhook | Care manager; consent-gated; webhook verified and deduplicated. | BE | 04B §10, §14 | Not started
M15-19 | 4 Events | OutreachRequested, OutreachDelivered, OutreachFailed, OutreachCompleted | Via the outbox; delivery receipts consumed through the inbox. | BE | 04B §12 | Not started
M15-20 | 5 Screens | S-12 Outreach Log & Composer | "Pending template" and "Undelivered" badges; consent scope; next permissible date; message previews. | FE | 04C S-12 | Not started
M15-21 | 5 Screens | Unclear-STOP queue | Care-manager queue for ambiguous opt-outs. | FE | RM FE-M15 | Not started
M15-22 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M15-23 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M15-24 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M15-25 | 6 Tests | Consent-gate tests | Without valid consent every command, dispatch and query path returns ZCARE_CONSENT_REQUIRED or ZCARE_CONSENT_REVOKED (HTTP 200 exception). | BE, QA | 04D §9.4; 04F §18 | Not started
M15-26 | 6 Tests | STOP and race tests | STOP during a pending send: nothing is sent; ambiguous STOP suppresses but keeps enrolment. | BE, QA | UAT-10, UAT-11 | Not started
M15-27 | 6 Tests | Webhook tests | Forged signature rejected; redelivery absorbed; placeholder copy marked until Privacy approval. | BE, SEC | UAT-16; RM R5 | Not started
M15-28 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M15-29 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-OUT-001..004, ZCR-MED-001. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M15-30 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M15-31 | 7 Docs | Demo journey evidence committed | Evidence of Journeys 13 and 20 (reminder sent; STOP stops all contact) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M15-32 | 8 Gate out | Done-when demonstrated | "STOP" halts all contact straight away, and a consent withdrawal always wins over a message about to be sent. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M15-33 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code; Privacy approval of all member-facing wording. | PRIV, PO | 04F §27, §30 | Not started
M15-34 | 8 Gate out | Release v0.15.0 tagged | Annotated tag v0.15.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M16 Outcomes
M16 · Outcomes & Proof | [8 empty] | ← Dashboard
Goal | Show results to payers and employers as totals only, hidden when the group is too small.
Owns | domains.outcome: zc_outcome_observation, zc_report_snapshot (mig-16)
Plan | Depends on M15 · Sprints S35–S36 · Screens S-17 · Release v0.16.0
Done when | Employers never see individuals, and groups under 10 are withheld, never estimated.
Progress | 0% | Tasks | 26 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M15 Engagement first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M16-01 | 0 Gate in | Confirm M15 is signed off | Dashboard shows M15 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M16-02 | 0 Gate in | Re-read this domain's specs | PRD §8.13, §12.7, §15; 04A INV-8; 04B §10–11; 04C S-17; ADD A7; ADR-008/009; mig-16. | BE, FE | AGENTS "Source precedence" | Not started
M16-03 | 1 Data | Map owned tables to JPA entities | zc_outcome_observation, zc_report_snapshot. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-16; 04D §11; ADR-0002 | Not started
M16-04 | 1 Data | Map append-only tables as insert-only | zc_report_snapshot: INSERT and SELECT only; a change is a new row (trigger and privilege already enforce it). | BE | 04D §11; mig-20 | Not started
M16-05 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M16-06 | 1 Data | Translate constraint violations to exception codes | ck_zc_report_employer_threshold → employer report needs a threshold; below threshold → ZCARE_AGGREGATE_THRESHOLD_NOT_MET (WARNING). | BE | 04D §9.3; 04B §6 | Not started
M16-07 | 2 Rules | Record outcomes against definitions | Measure code and version from the programme; the 10 founding measures. | BE | ZCR-OCM-001; ADR-008 | Not started
M16-08 | 2 Rules | Evidence classes kept apart | Activity, participation, operational, clinical, financial association, attributed impact; correlation is never called impact; no savings claims. | BE | ZCR-OCM-002, OCM-004 | Not started
M16-09 | 2 Rules | Report snapshots per audience | Internal, payer, provider, employer_aggregate; frozen figures with measure version. | BE | mig-16 | Not started
M16-10 | 2 Rules | Employer floor n ≥ 10 in code | Configuration may only raise it; withheld measures listed, never rounded or approximated; complementary suppression. | BE | ADD A7; ADR-009 | Not started
M16-11 | 2 Rules | Employer sees aggregates only | No member-level route for the employer role; audience tied to role. | BE, SEC | 04A INV-8; ZCR-PRI-002 | Not started
M16-12 | 2 Rules | Incomplete data and caveats | Incomplete figures flagged with a reason; admin adds caveats before publishing. | BE | ZCR-OCM-005; 04C J15 | Not started
M16-13 | 3 API | POST /outcomes:record, GET /programmes/{id}/proof | Programme admin records; proof is audience-filtered. | BE | 04B §10–11 | Not started
M16-14 | 4 Events | OutcomeRecorded | Via the outbox. | BE | 04B §12 | Not started
M16-15 | 5 Screens | S-17 Reports & Programme Proof | Withheld cells explained; measure version on every figure; "correlation" label; "Incomplete data" badge. | FE | 04C S-17 | Not started
M16-16 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M16-17 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M16-18 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M16-19 | 6 Tests | Employer boundary suite | n < 10 withheld; employer asking for payer audience gets 403; no individual data in any employer response. | BE, QA | UAT-12..14; 04F §18 | Not started
M16-20 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M16-21 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-OCM-001..005, ZCR-PRI-002. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M16-22 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M16-23 | 7 Docs | Demo journey evidence committed | Evidence of Journeys 15 and 16 (small group withheld on the employer view) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M16-24 | 8 Gate out | Done-when demonstrated | Employers never see individuals, and groups under 10 are withheld, never estimated. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M16-25 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code; Privacy confirmation of the threshold. | PRIV, PO | 04F §27, §30 | Not started
M16-26 | 8 Gate out | Release v0.16.0 tagged | Annotated tag v0.16.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M17 Audit
M17 · Audit & Security | [8 empty] | ← Dashboard
Goal | Give administrators a tamper-proof history of activity, and harden security.
Owns | domains.audit: zc_domain_audit, zc_security_event (mig-18)
Plan | Depends on M16 · Sprints S37–S38 · Screens S-20 · Release v0.17.0
Done when | History cannot be edited or deleted, and no serious security issue is open.
Progress | 0% | Tasks | 25 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M16 Outcomes first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M17-01 | 0 Gate in | Confirm M16 is signed off | Dashboard shows M16 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M17-02 | 0 Gate in | Re-read this domain's specs | PRD §9.2, §9.8, §9.12; 04A INV-7; 04B §5, §11, §18; 04C S-20; 04D §11; mig-18. | BE, FE | AGENTS "Source precedence" | Not started
M17-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-15 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M17-04 | 1 Data | Map owned tables to JPA entities | zc_domain_audit, zc_security_event. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-18; 04D §11; ADR-0002 | Not started
M17-05 | 1 Data | Map append-only tables as insert-only | zc_domain_audit, zc_security_event: INSERT and SELECT only; a change is a new row (trigger and privilege already enforce it). | BE | 04D §11; mig-20 | Not started
M17-06 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M17-07 | 2 Rules | Audit coverage review | Every material write in M03–M16 writes an audit row with actor, operation, previous and new state, correlation id. | BE | ZCR-AUD-001; 04A INV-7 | Not started
M17-08 | 2 Rules | Fixed operation vocabulary | The 26 approved operations; envelope auditTrail.operation uses the same values. | BE | 04D §11; OD-15 | Not started
M17-09 | 2 Rules | Audit query, metadata only | Search by member, actor, entity, correlation id and dates; never clinical content; permitted roles only. | BE | 04C S-20; PRD §9.8 | Not started
M17-10 | 2 Rules | Audited export | Every export writes an audit_export security event. | BE | 04B §11 | Not started
M17-11 | 2 Rules | Sign-in events | Keycloak authentication success, failure and lockout recorded as security events. | BE, SEC | RM BE-M17; mig-18 | Not started
M17-12 | 2 Rules | Security hardening | Dependency and secret scanning in CI; OWASP ZAP baseline; penetration test; High/Critical findings fixed. | SEC, OPS | RM BE-M17; STD DEP-07, SEC-07 | Not started
M17-13 | 3 API | GET /audit?filter[...] and export | Permitted roles only. | BE | 04B §11 | Not started
M17-14 | 5 Screens | S-20 Audit Query and security events | Metadata-only results; export logged; emergency-access banner. | FE | 04C S-20; RM FE-M17 | Not started
M17-15 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M17-16 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M17-17 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M17-18 | 6 Tests | Audit history suite | Append-only by privilege and trigger; sweep proves every write is audited; no PHI in audit responses. | BE, QA | 04F §18; UAT-15 | Not started
M17-19 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M17-20 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-AUD-001, ZCR-SEC-001/002, ZCR-PRI-001, ZCR-DAT-001, ZCR-PRV-003. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M17-21 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M17-22 | 7 Docs | Demo journey evidence committed | Evidence of Journey 17 (search history without seeing health data) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M17-23 | 8 Gate out | Done-when demonstrated | History cannot be edited or deleted, and no serious security issue is open. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M17-24 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code; security review and penetration test sign-off. | SEC, PO | 04F §27, §30 | Not started
M17-25 | 8 Gate out | Release v0.17.0 tagged | Annotated tag v0.17.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M18 Integration
M18 · Integration Persistence | [8 empty] | ← Dashboard
Goal | Every message to and from other systems is delivered, or clearly flagged if it fails.
Owns | domains.integration: zc_idempotency_key, zc_integration_outbox, zc_integration_inbox, zc_dead_letter (mig-19)
Plan | Depends on M17 · Sprints S39–S41 · Screens S-19 · Release v0.18.0
Done when | No failure is silent: every failed delivery appears as a task for an administrator.
Progress | 0% | Tasks | 27 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M17 Audit first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M18-01 | 0 Gate in | Confirm M17 is signed off | Dashboard shows M17 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M18-02 | 0 Gate in | Re-read this domain's specs | PRD §10.2–10.5, §10.15; 04A §7.15, §22.4; 04B §7, §12–15; 04C S-19; 04D §17–18; ADD A10–A11; mig-19. | BE, FE | AGENTS "Source precedence" | Not started
M18-03 | 0 Gate in | Close the open decisions needed here | Open Decisions sheet: OD-24, OD-25 marked Decided, with the ADR or doc that records each. | PO, BE | OD sheet | Not started
M18-04 | 1 Data | Map owned tables to JPA entities | zc_idempotency_key, zc_integration_outbox, zc_integration_inbox, zc_dead_letter. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-19; 04D §11; ADR-0002 | Not started
M18-05 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M18-06 | 1 Data | Translate constraint violations to exception codes | uq inbox (tenant, source, message id) → duplicate absorbed; uq_zc_idempotency_key → IDEMPOTENCY_KEY_CONFLICT. | BE | 04D §9.3; 04B §6 | Not started
M18-07 | 2 Rules | Outbox delivery job | Per tenant (iterate the registry); FOR UPDATE SKIP LOCKED; bounded retry with jittered backoff; then dead letter. | BE | 04D §17; RM trial M3 | Not started
M18-08 | 2 Rules | Inbox processing | Deduplicated on (tenant, source system, message id); idempotent handlers. | BE | 04D §17 | Not started
M18-09 | 2 Rules | Dead letters become tasks | Operational task for platform_admin; retry, correct-and-retry with reason, escalate or discard, with the outcome recorded. | BE | 04A §22.4; ADD A10 | Not started
M18-10 | 2 Rules | ZPS status feed | Outbound enrolment, participation, gap, referral, adherence, task and outcome status over signed webhooks. | BE | PRD §10.5; RM BE-M18 | Not started
M18-11 | 2 Rules | ZHEP feed, switched off | Built and tested against a simulation; flag off. | BE | RM BE-M18; RM R7 | Not started
M18-12 | 2 Rules | Keep evidence of failures | Original request and response kept; temporary and permanent failures separated; alerts on unresolved failures. | BE, OPS | PRD §10.15; ZCR-OPR-001 | Not started
M18-13 | 2 Rules | Expired-record tidy-up | Idempotency keys older than their expiry swept by the decided housekeeping mechanism. | BE, OPS | RM BE-M18; OD-25 | Not started
M18-14 | 2 Rules | Integration health and metrics | Queue depth, failure counts and dependency health per component; optional integrations never fail liveness. | BE, OPS | STD RES-05, LOG-06 | Not started
M18-15 | 3 API | Integration console endpoints | List, inspect and resolve dead letters; define in 04B first. | BE | OD-16 | Not started
M18-16 | 5 Screens | S-19 Integration & Ops Console | Scope of impact (which workflows, how many members); human reconciliation. | FE | 04C S-19 | Not started
M18-17 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M18-18 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M18-19 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M18-20 | 6 Tests | External-failure suite | For each port: down → retry → dead letter → task; duplicate inbound absorbed; nothing lost. | BE, QA | 04F §18; STD QA-07 | Not started
M18-21 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M18-22 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-INT-001..004, ZCR-AVL-001, ZCR-IOP-001, ZCR-OPR-001. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M18-23 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M18-24 | 7 Docs | Demo journey evidence committed | Evidence of Journey 19 (administrator resolves a failed delivery) under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M18-25 | 8 Gate out | Done-when demonstrated | No failure is silent: every failed delivery appears as a task for an administrator. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M18-26 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code. | PO | 04F §27, §30 | Not started
M18-27 | 8 Gate out | Release v0.18.0 tagged | Annotated tag v0.18.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M19 AI
M19 · AI (switched off) | [8 empty] | ← Dashboard
Goal | Prepare for future AI suggestions, switched off, with nothing depending on them.
Owns | domains.ai: zc_ai_recommendation, zc_ai_review (mig-17)
Plan | Depends on M18 · Sprints S42 · Screens Hidden AI panel · Release v0.19.0
Done when | Everything works with AI switched off, and checks prove no AI is called anywhere.
Progress | 0% | Tasks | 21 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M18 Integration first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M19-01 | 0 Gate in | Confirm M18 is signed off | Dashboard shows M18 at 100% and its Gate out rows are Done. Do not start this sheet before that. | PO | RM §2.2 | Not started
M19-02 | 0 Gate in | Re-read this domain's specs | PRD §8.16, §11; 04A §7.16, §19; 04E (all); mig-17. | BE, FE | AGENTS "Source precedence" | Not started
M19-03 | 1 Data | Map owned tables to JPA entities | zc_ai_recommendation, zc_ai_review. Identity ids never supplied; @Version on row_version; tenant_id and created_* not updatable; entities stay inside the service layer. | BE | mig-17; 04D §11; ADR-0002 | Not started
M19-04 | 1 Data | Repositories and Specifications | Spring Data repositories and <X>Specifications for search; every query runs inside the tenant context (RLS); lists are paged thin projections. | BE | 04F §8; STD JPA-11 | Not started
M19-05 | 1 Data | Translate constraint violations to exception codes | ck_zc_ai_advisory → every recommendation advisory; review decision other than accepted needs a rationale. | BE | 04D §9.3; 04B §6 | Not started
M19-06 | 2 Rules | Flags default off | zcare.ai.enabled=false; per-tenant, per-use-case flags in configuration scope "features". | BE | RM BE-M19; 04F §13; 04E §20.5 | Not started
M19-07 | 2 Rules | ModelPort interface only | No adapter, no model SDK dependency, no network call. | BE | RM BE-M19; 04F §12 | Not started
M19-08 | 2 Rules | Recommendation and review records | Advisory only; human review accepted, modified or rejected with rationale. | BE | 04E §4; mig-17 | Not started
M19-09 | 2 Rules | Prohibited uses documented | No diagnosis, prescribing, plan approval, referral orders or payer decisions; no PHI to hosted APIs. | BE, PO | 04E §3, §6; ZCR-AID-004 | Not started
M19-10 | 5 Screens | No AI affordances while off | Pilot screens unchanged; AI panel renders only if a flag is on. | FE | 04C §13; RM FE-M19 | Not started
M19-11 | 6 Tests | Unit tests for every rule in step 2 | Each state transition and invariant has a behaviour-named test (JUnit 5, AssertJ, Mockito). | BE | 04F §18; STD QA-01, QA-06 | Not started
M19-12 | 6 Tests | Integration tests on PostgreSQL 16 as zc_app | Testcontainers; repositories, constraint-to-code mapping and tenant isolation proven through this domain's tables. | BE, QA | 04F §18; STD QA-02 | Not started
M19-13 | 6 Tests | Security matrix for each endpoint | 401 without or with an expired token; 403 for a wrong role; another tenant's record refused and a security event written. | BE, QA | 04F §20; STD QA-04 | Not started
M19-14 | 6 Tests | AI-off proofs | ArchUnit: nothing calls ModelPort in production code; full suite green with all flags off; flag-off restores the non-AI path. | BE, QA | 04E §20.7, §21 | Not started
M19-15 | 7 Docs | Contracts updated in the same PR | openapi/zcare-openapi.yaml and asyncapi/zcare-asyncapi.yaml match the code; each new endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric (score in the PR). | BE | 04F §9, §30; 04B §1 | Not started
M19-16 | 7 Docs | Knowledge base updated | package-info (owned tables), docs/database/migration-plan.md, docs/architecture/overview.md, traceability rows for ZCR-AID-001..006. | BE | ADR-0002 r3; GUIDE §17; 04F §31 | Not started
M19-17 | 7 Docs | CHANGELOG [Unreleased] lines written | One line per change for readers outside the team, including Database and Configuration sections. | BE | STD REL-03 | Not started
M19-18 | 7 Docs | Demo journey evidence committed | Evidence of full regression with all AI flags off under docs/demo/evidence/ with screenshots. | QA, FE | AGENTS "Journey evidence" | Not started
M19-19 | 8 Gate out | Done-when demonstrated | Everything works with AI switched off, and checks prove no AI is called anywhere. Shown end to end (server and screens) at the sprint demo. | PO | RM §3 | Not started
M19-20 | 8 Gate out | Reviews signed off | Code review with a named reviewer for security-sensitive code. | PO | 04F §27, §30 | Not started
M19-21 | 8 Gate out | Release v0.19.0 tagged | Annotated tag v0.19.0 from a green pipeline; CHANGELOG section dated; next SNAPSHOT set. Dashboard now shows 100%. | BE | STD REL-01, REL-04, REL-07 | Not started

## M20 Acceptance
M20 · Testing & Acceptance | [8 empty] | ← Dashboard
Goal | Test the whole system end to end and get the business to sign it off.
Owns | Whole service and web app
Plan | Depends on M19 · Sprints S43–S48 · Screens All · Release v1.0.0
Done when | All tests pass, users sign off, no serious defects remain, and the go/no-go decision is recorded.
Progress | 0% | Tasks | 15 | Done or N/A | 0 | Blocked | 0 | State | Not started
LOCKED: finish M19 AI first. Do not start work on this sheet.
# | Step | Task | Detail / done when | Team | Ref | Status | Owner | Date done | Notes / evidence
M20-01 | 0 Gate in | Confirm M19 is signed off | Dashboard shows M01–M19 at 100%. | PO | RM §2.2 | Not started
M20-02 | 0 Gate in | Fix the journey list | Agree which journeys the automated run covers (roadmap says 13; 04C lists 20). | PO, QA | OD-27 | Not started
M20-03 | 5 Screens | Automated journeys (Playwright) | Every agreed journey passes end to end. | FE, QA | RM FE-M20 | Not started
M20-04 | 5 Screens | Accessibility and browsers | axe WCAG 2.1 AA; Lighthouse; browser matrix; one manual screen-reader pass per journey. | FE, QA | RM FE-M20; 04C §14 | Not started
M20-05 | 6 Tests | All 04F test suites green in CI | Unit, integration (04D §25.1), contract, structural, tenant isolation, consent gate, employer boundary, audit history, external failure, e2e, traceability. | QA, BE | 04F §18 | Not started
M20-06 | 6 Tests | API standard audit | Every endpoint scores at least 18/22 on the ENG-STD-SB-001 rubric. | QA | RM BE-M20; 04B §1 | Not started
M20-07 | 6 Tests | Security tests | OWASP ZAP clean; dependency and secret scans clean; penetration-test findings closed. | SEC | RM BE-M20 | Not started
M20-08 | 6 Tests | Performance and resilience | Queue p95 < 500 ms at 100× synthetic volume; two-tenant load probe; chaos-lite. | QA, OPS | 04F §22 | Not started
M20-09 | 6 Tests | Privacy tests | No-PHI-in-logs leak test; employer boundary; consent protection. | QA, PRIV | 04F §21 | Not started
M20-10 | 6 Tests | UAT with real roles | 25 scripts: UAT-01..16 (required) and UAT-20..28 (diabetes pathway), mapped to Must-Have ZCR ids. | QA, PO | UAT; PRD App. F.2 | Not started
M20-11 | 7 Docs | Gate 4 conditions met | Privacy wording approved; retention rules (DEC-015); Aga Khan content package; security review; provider contract (DEC-011); monitoring and recovery tested. | PO, PRIV, CLIN, SEC | GUIDE §13; RM R5, R6 | Not started
M20-12 | 7 Docs | Production readiness | No [SYNTHETIC] content reachable by a real tenant; rollback image identified; runbook and alerts in place. | OPS, BE | 04F §27 | Not started
M20-13 | 7 Docs | Release notes cite requirement ids | Notes for integrators list API, migrations, configuration and ZCR ids. | PO, BE | STD REL-06; GUIDE §13 | Not started
M20-14 | 8 Gate out | Sign-off and go/no-go | Founder, Care Operations and Clinical (Aga Khan) sign; decision recorded. | PO, CLIN | RM BE-M20; UAT | Not started
M20-15 | 8 Gate out | Release v1.0.0 tagged | First production release; from here VER-04 applies in full. | BE | STD VER-03, REL-04 | Not started

## Open Decisions
Open Decisions
Conflicts and gaps found in the documents. Close every row a milestone needs (column D) before starting it: set Status to Decided and name the ADR or document that records the decision. Conflicts are escalated, never silently resolved (AGENT_GUARDRAILS).
ID | Decision or conflict | Sources | Needed by | Suggested direction | Status | Owner | Decision and record (ADR / doc) | Date
OD-01 | Response style: 04B envelope (business errors as HTTP 200) or the standard's RFC 9457 Problem Details | 04B §5–6; AGENTS; STD WEB-02, ERR-02 | M02 | Record ADR-0005 adopting the 04B envelope (the standard allows an envelope when an ADR records it). | Open
OD-02 | Tenant source: X-Tenant-Id header (04B §3) or token claim (tenant/package-info, trial roadmap) | 04B §3; tenant/package-info | M02 | Token is the authority; header spoofing gives 403 plus tenant_violation_attempt. | Open
OD-03 | Base path: /{tenant}/zcare/v1 (04B §4) or /api/v1 (STD API-01) | 04B §4, §16; STD API-01 | M02 |  | Open
OD-04 | Canon written for Python (04F, AGENTS, ARCHITECTURE); map its layers to ADR-0002 packages and update the canon | 04F §3–6; ADR-0002 | M02 |  | Open
OD-05 | Build: roadmap says Maven multi-module; ADR-0002 chose one project | RM BE-M2; ADR-0002 | M02 | Confirm ADR-0002 with the roadmap owner. | Open
OD-06 | Version control and CI: no git repository yet; roadmap names GitHub Actions | RM BE-M2; STD C.5 | M01, M02 |  | Open
OD-07 | Spring Boot 3.2.2 is past open-source support; choose a supported version | ADR-0001; STD DEP-02 | M02 |  | Open
OD-08 | Where M2's audit, idempotency and outbox writers live (tables belong to M17/M18 domains) | RM BE-M2; ADR-0002 r5 | M02 |  | Open
OD-09 | Home for PayerPort, OutreachPort, ProviderPort and ModelPort (ADR-0002 has none) | ARCHITECTURE; 04F §2; STD INT-04 | M05 | Avoid the name clash with domains.integration. | Open
OD-10 | Republish the API description with numeric ids | RM R1; ADR-0004 | M02 |  | Open
OD-11 | Sign-in details with the platform team (Keycloak realm, clients, claims) | RM R4 | M02 |  | Open
OD-12 | zc_user.password_hash is NOT NULL although ZCare keeps no passwords | ADR-0004; RM §1.1 | M03 |  | Open
OD-13 | zc_tenant_whatsapp.access_token stored in the database although secrets live only on servers | ADR-0004; RM §1.1 | M03, M15 |  | Open
OD-14 | How tenants are provisioned (zc_app can only read zc_tenant) | mig-03; RM M3 | M03 |  | Open
OD-15 | Approved lists still missing: care models, priority-tier names, 26 audit operations | RM R3; ADR-0004 | M04, M08, M17 | Use editable lists until approved. | Open
OD-16 | Endpoints missing from 04B: admin, members list, preferences, consent re-prompt, cohort release, plan submit, task accept/cancel/reassign/escalate, observation invalidate, console | 04B; 04C | M03, M05, M06, M07, M08, M09, M10, M13, M18 | Add each to 04B and OpenAPI before its milestone starts. | Open
OD-17 | Addendum endpoints and code not in the 04B registry (request-changes, reject, record-clinical-approval, ZCARE_THRESHOLD_REVIEW_REQUIRED) | ADD Part B, E; 04B §6 | M04, M09, M13 |  | Open
OD-18 | OpenAPI and AsyncAPI files that 04B calls complete do not exist | 04B; 04F §9 | M02 | Create them and diff in CI. | Open
OD-19 | Consent revocation: 04A says suspend, ADD A5 says exact STOP withdraws and revokes | 04A §16; ADD A5 | M07 |  | Open
OD-20 | Care-plan approver: 04A §7.5 allows clinician or care manager; 04A §22.2, ADD E and the roadmap say clinician only, never the author | 04A; ADD E; RM §1.2 | M09 |  | Open
OD-21 | Who may suppress and who may close a care gap; second pair of eyes | 04C §20 #6; ADD C1, C2 | M14 |  | Open
OD-22 | Privacy approval of WhatsApp wording (go-live condition) | RM R5; 04A §21 | M15, M20 | Build with marked placeholders. | Open
OD-23 | Provider Portal contract (DEC-011) | PRD App. E; 04B §21 | M11 |  | Open
OD-24 | ZPS status-feed format and ZHEP interface | RM R7 | M15, M18 | Test against simulations meanwhile. | Open
OD-25 | Mechanism for the housekeeping sweep (zc_housekeeping is NOLOGIN) | mig-19; RM BE-M18 | M18 |  | Open
OD-26 | Retention rules (DEC-015) and Aga Khan clinical content (thresholds) | RM R6; ADD A8 | M13, M20 | Synthetic values until supplied. | Open
OD-27 | Which journeys the final automated run covers (roadmap 13, 04C 20) | RM FE-M20; 04C §5 | M20 |  | Open
OD-28 | Event data_classification casing: PHI (04B) or phi (04D) | 04B §12; 04D §17 | M02 |  | Open
OD-29 | SLA values for tasks and threshold reviews are unset | 04C S-01, S-14 | M10, M13 |  | Open
OD-30 | Privacy approval record for the assisted-consent script | ADD A4 | M07 |  | Open